## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme. | SM/14838 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Digha Water Supply Scheme (Eastern Zone) under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000442/2021-2022 | .1651/TD | 20/01/2022 | 09/02/2022 | HORIZEN | 4.21 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme. | SM/14838 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 2640/TD | 13/10/2023 | 13/10/2023 | Resource Division | 13.39 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme. | SM/14838 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 2066/TD | 28/08/2023 | 28/08/2023 | Resource Division | 106.76 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme. | SM/14838 | Augmentation | Quotation for new service connection at T/W-III of Digha Eastern zone under MMD, PHE Dte, Block-Ramnagar-I,DIGHA CCC Application no-2004812582 CON ID-204351921 |  |  | BILL/01586/2024-2025 | C072438488216 | 23/07/2024 | 23/07/2024 | WBSEDCL | 0.88 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme. | SM/14838 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2052 nos) under JJM with allied work for Digha Augmentation (Eastern Zone) PWSS within Ramnagar-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000493/2023-2024 | 1591/TD | 21/07/2023 | 01/12/2025 | ATCO ENTERPRISE | 642.85 | 0 | 0 | 40
6 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme. | SM/14838 | Augmentation | Repairing & renovation of Switch Room , existing boundary wall, Store Room, OHR 250 cum. capacity 20 m height, & Accommodate FHTC (125 Nos) under JJM with allied work for Digha Augmentation (Eastern Zone ) Water Supply Scheme under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000323/2024-2025 | 3219/TD | 01/10/2024 | 01/12/2025 | M/S. NEW DINDA ENTERPRISE | 28.09 | 0 | 0 | 65
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme. | SM/14838 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme within Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001996/2022-2023 | 900/W/MMD | 27/03/2023 | 30/04/2025 | S.S.GHORAI | 25.26 | 0 | 0 | 100
Total | [13 empty] | 821.44 | 0 | 0