## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-I | SM/14839 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bathuary Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000460/2022-2023 | 1859/TD | 21/11/2022 | 11/12/2022 | ASTER CONSULTANCY | 3.3 | 2.95 | 89.3 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-I | SM/14839 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 2080/TD | 28/08/2023 | 28/08/2023 | Resource Division | 14.36 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-I | SM/14839 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 3012/TD | 29/11/2023 | 29/11/2023 | Resource Division | 0.14 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-I | SM/14839 | Augmentation | Laying distribution pipe line, Repair of Pump House , Repair Boundary Wall , land development for approch road & Accommodate FHTC (70 nos) under JJM with allied work for Bathuari (Zone-I) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000648/2023-2024 | 2600/TD | 10/10/2023 | 31/12/2025 | DILIP KUMAR GHOSH | 110.33 | 84.13 | 76.25 | 82
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Bathuari Zone-I | SM/14839 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at at different PWSS of Block Egra - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000073/2023-2024 | 1242/W/MMD | 28/04/2023 | 31/05/2025 | BHABANI PRASAD MANNA | 84.29 | 0 | 0 | 70
Total | [13 empty] | 212.42 | 87.07 | 40.99