## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-2 | SM/14840 | Augmentation | Laying distribution pipe line & Accommodate FHTC (7 Nos) under JJM with allied work for Chirulia-Chatla (Zone-II) PWSS within Egra-I Block under Digha Sub-Division of Tamluk Division ,PHED , Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000262/2023-2024 | 542/TD | 12/05/2023 | 11/07/2023 | SUBHENDU HAZRA | 71.29 | 60.07 | 84.25 | 93
2 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-2 | SM/14840 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chirulia Chatla Water Supply Scheme under Tamluk Division, PHE Dte. ( PART- II ) | Assistant Engineer | Junior Engineer | ORD/000966/2022-2023 | 1056/TD | 18/08/2022 | 07/09/2022 | ASTER CONSULTANCY | 4.01 | 4.01 | 100 | 100
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Chirulia-Chatla Zone-2 | SM/14840 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Egra - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000050/2023-2024 | 1207/W/MMD | 25/04/2023 | 31/12/2025 | BHABANI PRASAD MANNA | 59.85 | 0 | 0 | 20
4 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-2 | SM/14840 | Augmentation | Renovation & Repairing of existing pump house at 2nd T/W site of Chirulia Chatla Zone-II Water Supply Scheme within Egra-I Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000613/2024-2025 | 463/TD | 04/02/2025 | 04/06/2025 | RADHAKRISHNA TRADERS | 7.79 | 0 | 0 | 100
Total | [13 empty] | 142.93 | 64.07 | 44.83