## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-I | SM/14841 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme under Tamluk Division, PHE Dte. ( PART- I ) | Assistant Engineer | Junior Engineer | ORD/000967/2022-2023 | 1057/TD | 18/08/2022 | 07/09/2022 | ASTER CONSULTANCY | 3.6 | 2.95 | 81.98 | 100
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-I | SM/14841 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000052/2023-2024 | 1216/W/MMD | 25/04/2023 | 30/09/2025 | BHABANI PRASAD MANNA | 83.38 | 0 | 0 | 34
3 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-I | SM/14841 | Augmentation | Laying distribution pipe line, Accommodate FHTC ( 69 Nos) under JJM with allied work for KANPUR (Z-I) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000611/2023-2024 | 2255/TD | 05/09/2023 | 04/11/2023 | BASANTA KUMAR MAITY | 85.65 | 60.27 | 70.37 | 60
4 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-I | SM/14841 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000110/2023-2024 | 3013/TD | 29/11/2023 | 29/11/2023 | Resource Division | 0.43 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-I | SM/14841 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 2081/TD | 28/08/2023 | 28/08/2023 | Resource Division | 13.54 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-I | SM/14841 | Augmentation | Laying distribution pipe line (Left out), Repair and Renovation Pump House, Boundary Wall , 450 Cum OHR & Accommodate Balance FHTC ( 65 Nos) under JJM with allied work for KANPUR (Zone-I) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. |  |  | ORD/000237/2024-2025 | 2676/TD | 22/08/2024 | 06/10/2024 | MAITY CONSTRUCTION | 87.84 | 0 | 0 | 0
Total | [13 empty] | 274.44 | 63.23 | 23.04