## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-II | SM/14842 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Piped Water Supply Scheme for Sankarpur Zone-II Ramnagar I Blockunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/002046/2022-2023 | 887/W/MMD | 27/03/2023 | 23/09/2023 | R.S. ENTERPRISE | 11.4 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-II | SM/14842 | Augmentation | Laying distribution pipe line & Accommodate FHTC ( 79 Nos) under JJM with allied work for SANKARPUR (Zone-II) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000145/2023-2024 | 287/TD | 20/04/2023 | 10/05/2023 | BUNBA CONSTRUCTION | 16.35 | 14.59 | 89.27 | 90
3 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-II | SM/14842 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone- II) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000329/2023-2024 | 739/TD | 25/05/2023 | 14/06/2023 | ASTER CONSULTANCY | 3.46 | 3.41 | 98.77 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-II | SM/14842 | Augmentation | Laying distribution pipe line, renovation of Pump House, Boundary Wall 400 Cum OHR & Accommodate balance FHTC ( 42 Nos) under JJM with allied work for SANKARPUR (Zone-II) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000118/2024-2025 | 1914/TD | 07/06/2024 | 05/12/2024 | GHOSH CONSTRUCTION | 38.32 | 0.43 | 1.12 | 100
Total | [13 empty] | 69.52 | 18.43 | 26.52