## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | 1 (One) No. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/14843 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001988/2022-2023 | 895/W/MMD | 27/03/2023 | 23/09/2023 | SUBHASIS ROY | 11.84 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/14843 | Augmentation | Laying of 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at 1(One) no. Boosting Tube Well of Source Augmentation of Bamunia & its adjoining mouzas Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer |  | ORD/000368/2023-2024 | 999/TD | 05/06/2023 | 05/07/2023 | GIRI CONSTRUCTION | 3.39 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/14843 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 340/TD | 26/04/2023 | 26/04/2023 | Resource Division | 5.21 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/14843 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme within Contai- II ( Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer |  | ORD/000111/2023-2024 | 241/TD | 19/04/2023 | 19/05/2023 | GITA ENTERPRISE | 7.54 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/14843 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150 mm. dia. x 230 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme within Contai-II (DESOPRAN) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme within Contai-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000021/2023-2024 | 119/TD | 06/04/2023 | 09/03/2025 | B. K. ENTERPRISE | 53.77 | 0 | 0 | 75
Total | [13 empty] | 81.74 | 0 | 0