## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/14844 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 341/TD | 26/04/2023 | 26/04/2023 | Resource Division | 4.77 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/14844 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001986/2022-2023 | 894/W/MMD | 27/03/2023 | 23/09/2023 | SUBHASIS ROY | 11.84 | 11.09 | 93.64 | 85
3 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/14844 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150 mm. dia. x 230 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme within Contai-II (DESOPRAN) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme within Contai-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000021/2023-2024 | 119/TD | 06/04/2023 | 09/03/2025 | B. K. ENTERPRISE | 53.77 | 12.84 | 23.88 | 75
4 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/14844 | Augmentation | Constrution of Boundary wall (as per Departmental Desigh & Drawing) And,Augmentation of Silampur Scheme within Contai-II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000303/2023-2024 | 600/TD | 17/05/2023 | 16/06/2023 | M/S SOURAV MAHAPATRA | 7.01 | 4.5 | 64.24 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/14844 | Augmentation | Laying of 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at 1(One) no. Boosting Tube Well of Source Augmentation of Silampur & its adjoining mouzas Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000213/2023-2024 | 480/TD | 10/05/2023 | 09/06/2023 | JASODA ENTERPRISE | 3.27 | 1.05 | 32.19 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/14844 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Source Augmentation of Silampur W/S Scheme within Contai - I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000214/2023-2024 | 481/TD | 10/05/2023 | 09/07/2023 | THE GODFATHER TRADING COMPANY | 3.67 | 3.56 | 97.17 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/14844 | Augmentation | Instalation of display Board at different work site of Silampur, Uttar Khasda, Barchunfali, Uttar Charaikhia Retrofitting PWSS in Contai - I Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer |  | ORD/001176/2023-2024 | 2331/CSD | 29/12/2023 | 13/01/2024 | SAURAV HAZRA | 0.83 | 0.83 | 100 | 100
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/14844 | Augmentation | Electric Quotation for SILAMPUR Water Supply Scheme T/W-III, (Ref. ID-204134606) |  |  | BILL/02997/2023-2024 | BP-2023-24-361 | 24/11/2023 | 24/11/2023 | WBSEDCL | 3.71 | 0 | 0 | 0
Total | [13 empty] | 88.86 | 33.88 | 38.12