## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/14845 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at 4th TW site for Augmentation of Mukutshila Zone-II PWSS within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-44.00 mtr.)For Low Land. | Assistant Engineer | Junior Engineer | ORD/000438/2023-2024 | 1421/TD | 12/07/2023 | 11/08/2023 | M/S. NEW DINDA ENTERPRISE | 6.93 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/14845 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer | Junior Engineer | ORD/000228/2023-2024 | 474/TD | 10/05/2023 | 09/07/2023 | GIRI ENTERPRISE | 3.71 | 3.67 | 98.82 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/14845 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting TW site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer | Junior Engineer | ORD/000230/2023-2024 | 476/TD | 10/05/2023 | 09/07/2023 | GIRI CONSTRUCTION | 3.71 | 3.7 | 99.72 | 100
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/14845 | Augmentation | Electric quotation for Mukutshila PWSS Zone-II, Tube Well-II WS Scheme (Ref. ID 203933340) |  |  | BILL/00418/2022-2023 |  | 25/03/2023 | 25/03/2023 | WBSEDCL | 0.37 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/14845 | Augmentation | Electric quotation for Mukutshila PWSS Zone-II, Tube Well-II WS Scheme (Ref. ID 203933340) |  |  | BILL/00106/2023-2024 | BP-2023-24-25 | 04/05/2023 | 04/05/2023 | WBSEDCL | 0.37 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/14845 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II water supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -N) | Assistant Engineer | Junior Engineer | ORD/000456/2023-2024 | 1501/TD | 17/07/2023 | 06/08/2023 | THE GODFATHER TRADING COMPANY | 5.24 | 3.2 | 61.03 | 65
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/14845 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 4th TW site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer | Junior Engineer | ORD/000229/2023-2024 | 475/TD | 10/05/2023 | 09/07/2023 | GIRI ENTERPRISE | 3.71 | 3.69 | 99.35 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/14845 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Boosting TW site for Augmentation of Mukutshila Zone-II PWSS within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-44.00 mtr.)For Low Land | Assistant Engineer | Junior Engineer | ORD/000317/2023-2024 | 663/TD | 19/05/2023 | 18/06/2023 | GIRI CONSTRUCTION | 6.94 | 5.89 | 84.91 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/14845 | Augmentation | Rising main 200mm dia DI(K9) Rising main pipeline with specials and other allied works at 3rd Tube Well Site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000394/2023-2024 | 1083/TD | 08/06/2023 | 28/06/2023 | M/S. NEW DINDA ENTERPRISE | 5.07 | 3.28 | 64.67 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/14845 | Augmentation | Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Mukutshila Zone-II PWSS within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-44.00 mtr.)For Low Land | Assistant Engineer | Junior Engineer | ORD/000318/2023-2024 | 664/TD | 19/05/2023 | 18/06/2023 | DAS ENTERPRISE | 6.91 | 5.07 | 73.44 | 100
11 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/14845 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001471/2022-2023 | 209/W/MMD | 10/02/2023 | 09/08/2023 | SUBHASIS ROY | 11.84 | 9.44 | 79.77 | 70
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/14845 | Augmentation | Laying of 150mm dia DI(K9) Rising main pipeline with specials and other allied works at 1(One) no. Boosting Tubewell for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri - I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000233/2023-2024 | 477/TD | 10/05/2023 | 05/03/2024 | KOUSHIK MALLICK | 3.22 | 0 | 0 | 100
Total | [13 empty] | 58.03 | 37.95 | 65.39