## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Contai Saline Area Zone-IV Part-I Piped Water Supply Scheme | SM/15034 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Contai Saline Area Zone-IV Part-I Piped Water Supply Scheme Deshopran Block under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001983/2022-2023 | 891/W/MMD | 27/03/2023 | 23/09/2023 | GANGULY ENGINEERING CO. | 23.69 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-I Piped Water Supply Scheme | SM/15034 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. [PART-I] | Assistant Engineer | Junior Engineer | ORD/000453/2022-2023 | .1853/TD | 21/11/2022 | 11/12/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.61 | 3.2 | 88.49 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-I Piped Water Supply Scheme | SM/15034 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 2093/TD | 29/08/2023 | 29/08/2023 | Resource Division | 69.1 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-I Piped Water Supply Scheme | SM/15034 | Augmentation | Sinking of Tubewell, 250 cum OHR (Intze type with pile foundation), Laying distribution pipe line, Soil investigation, Pump House, Boundary wall, Rising Main & Accommodate FHTC (1807 nos) under JJM with allied work for Augmentation of Contai Saline Area Zone-IV PART-I PWSS in Deshapran Block within Contai Sub-Division under Tamluk Division, PHE Dte. |  |  | ORD/000852/2023-2024 | 897/TD | 11/03/2024 | 07/09/2024 | SRIMANTA KUMAR MAITY | 428.55 | 0 | 0 | 0
Total | [13 empty] | 524.95 | 3.2 | 0.61