## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Astichak (Zone-II) PWSS | SM/15035 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Astichak Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000858/2021-2022 | 1471/TD | 03/01/2022 | 23/01/2022 | APEX ENGINEERING | 4.75 | 4.75 | 100 | 100
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Astichak (Zone-II) PWSS | SM/15035 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Astichak (Zone-II) PWSS Egra II Block under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001982/2022-2023 | 890/W/MMD | 27/03/2023 | 31/07/2025 | M/S B.M. ELECTRICAL | 23.7 | 15.94 | 67.25 | 40
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Astichak (Zone-II) PWSS | SM/15035 | Augmentation | Proposed Rising main and interconnection with OHR of ASTICHAK (Z-II ) & its adjoining moujas Water Supply Scheme within Egra-II Dev. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000834/2023-2024 | 3326/TD | 27/12/2023 | 23/02/2026 | ONKAR ENTERPRISE | 515.99 | 401.82 | 77.87 | 98
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Astichak (Zone-II) PWSS | SM/15035 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 2079/TD | 28/08/2023 | 28/08/2023 | Resource Division | 49.99 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Astichak (Zone-II) PWSS | SM/15035 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000104/2023-2024 | 3007/TD | 29/11/2023 | 29/11/2023 | Resource Division | 13.53 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Astichak (Zone-II) PWSS | SM/15035 | Augmentation | Quotation Bill for New Service connection at T/W NO-III Of ASTICHAK ZII W/S Scheme under MMD, PHE, Dte. Block- EGRA II, WBSEDCL SUPPLY OFFICE: BALIGHAIC.C.C. Ref. Memo No- 2004749715/QUOT/03 DT. 05-06-2024 Application NO- 2004749715 Application type-New connection Consumer Id- 204317619 |  |  | BILL/01229/2024-2025 | BP-2024-25-299 | 18/06/2024 | 18/06/2024 | WBSEDCL | 5.53 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Astichak (Zone-II) PWSS | SM/15035 | Augmentation | Drum sheet piling work, Canal Crossing Structure for Distribution pipe line, Supply and delivery of different dia D.I. specials, Repairing & renovation of OHR (350 CUM), Repairing & renovation of existing H/W site Pump House & 2nd TW site Pump house with allied works under JJM for Augmentation of Astichak Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000640/2024-2025 | 852/TD | 19/03/2025 | 28/04/2025 | ONKAR ENTERPRISE | 78.51 | 0 | 0 | 100
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Astichak (Zone-II) PWSS | SM/15035 | Augmentation | Quotation Bill for New Service connection at T/W NO-IV, ZONE-II Of ASTICHAK W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2005050851/QUOT/03/963 DT. 20-01-2025 Application NO- 2005050851 Application type-New connection Consumer Id- 204501207 |  |  | BILL/04253/2024-2025 | C032554613786 | 17/03/2025 | 17/03/2025 | WBSEDCL | 4.19 | 0 | 0 | 0
Total | [13 empty] | 696.18 | 422.5 | 60.69