## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/15036 | Augmentation | Augmentation of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura-I Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 2558/TD | 24/01/2023 | 25/03/2023 | TARUN KOLEY | 73.36 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Central Drilling | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/15036 | Augmentation | Providing drilling crew and allied works for construction of Tube Well (300mm x 200mm x 230mtrs. Depth) by utilising Departmental Machineries for Gobindanagar PWSS 1ST Boosting TW, Z-I, Panskura - I Block under Purba Medinipur District, CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000461/2022-2023 | 2113/CDD | 02/03/2023 | 01/04/2023 | PADMA ENGINEERING & CO. | 17.76 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/15036 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 344/TD | 26/04/2023 | 26/04/2023 | Resource Division | 13.24 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/15036 | Augmentation | Electric Quotation for GOBINDANAGAR (ALALPARA)Water Supply Scheme Z-II, T/W-II (Ref. ID-204048367) |  |  | BILL/01815/2023-2024 | BP-2023-24-198 | 18/08/2023 | 18/08/2023 | WBSEDCL | 3.31 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/15036 | Augmentation | Electric Quotation for GOBINDANAGAR, Water Supply Scheme T/W-I, Zone-I (Ref. ID-204056032) |  |  | BILL/01754/2023-2024 | BP-2023-24-177 | 08/08/2023 | 08/08/2023 | WBSEDCL | 2.92 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/15036 | Augmentation | Electric Quotation for GOBINDANAGAR Water Supply Scheme Z-II, T/W-III (Ref. ID-204048353) |  |  | BILL/01814/2023-2024 | BP-2023-24-197 | 18/08/2023 | 18/08/2023 | WBSEDCL | 12.55 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/15036 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1(One)) No. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001395/2023-2024 | 3042/W/MMD | 17/11/2023 | 01/04/2025 | SHIVAM ENTERPRISE | 13.68 | 0 | 0 | 80
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/15036 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/002000/2022-2023 | 902/W/MMD | 27/03/2023 | 23/09/2023 | M/S EMMESS | 40.78 | 0 | 0 | 70
9 | PURBA MEDINIPUR |  | Tamluk Division | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/15036 | Augmentation | Name of Work: Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Gobindanagar W/S Scheme within Panskura-I Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Dakshin Mechogram W/S Scheme within Panskura-I Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000019/2023-2024 | 117/TD | 06/04/2023 | 16/05/2023 | AQUATECH ENGINEER | 37.12 | 0 | 0 | 100
10 | PURBA MEDINIPUR |  | Midnapore Mechanical | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/15036 | Augmentation | Additional service connection charge at Gobindanagar, Zone-II, TW-IV Chiara, Chiara, Gobindanagar, Golghat Panskura Ref ID-860294542 Application ID-100000102262 Panskura CCC |  |  | BILL/04383/2023-2024 | BP-2023-24-827 | 13/03/2024 | 13/03/2024 | WBSEDCL | 1.83 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Midnapore Mechanical | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/15036 | Augmentation | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 29/08/2024 | S.S.GHORAI | 2.12 | 0 | 0 | 50
12 | PURBA MEDINIPUR |  | Tamluk Division | 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/15036 | Augmentation | 3(Three) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room, Laying of Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Gobindanagar Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000133/2023-2024 | 269/TD | 20/04/2023 | 10/12/2024 | M/S. S. A. CONSTRUCTION | 49.64 | 0 | 0 | 100
Total | [13 empty] | 268.3 | 0 | 0