## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Tamluk | Tamluk Division | TULIA AND ADJOINING MOUJAS PWSS | SM/15037 | New | Material Requisition To Resource Division |  |  | RTOR000344/2022-2023 | 3018/TD | 27/02/2023 | 27/02/2023 | Resource Division | 24.12 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | TULIA AND ADJOINING MOUJAS PWSS | SM/15037 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for TULIA AND ADJOINING MOUJAS PWSS Tamluk Block under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001977/2022-2023 | 888/W/MMD | 27/03/2023 | 23/09/2023 | M.D.ENTERPRISE | 23.65 | 11.02 | 46.62 | 35
3 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | TULIA AND ADJOINING MOUJAS PWSS | SM/15037 | New | Tulia W/S scheme Application no.-2004555235 Ref.-204184819 |  |  | BILL/03534/2023-2024 | BP-2023-24-621 | 07/02/2024 | 07/02/2024 | WBSEDCL | 16.04 | 0 | 0 | 0
Total | [13 empty] | 63.81 | 11.02 | 17.28