## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Astichak (Zone-I) PWSS | SM/15462 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Astichak Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000856/2021-2022 | 1472/TD | 03/01/2022 | 23/01/2022 | APEX ENGINEERING | 3.99 | 3.99 | 100 | 100
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Astichak (Zone-I) PWSS | SM/15462 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Astichak (Zone-I) PWSS Egra II Block under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001981/2022-2023 | 889/W/MMD | 27/03/2023 | 23/09/2023 | M.D.ENTERPRISE | 23.65 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Astichak (Zone-I) PWSS | SM/15462 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC (291 nos) under JJM with allied work for ASTICHAK (ZONE-I) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000635/2023-2024 | 2444/TD | 19/09/2023 | 26/11/2026 | HALDIA DEVELOPMENT CONSTRUCTION | 446.88 | 0 | 0 | 55
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Astichak (Zone-I) PWSS | SM/15462 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 2078/TD | 28/08/2023 | 28/08/2023 | Resource Division | 24.42 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Astichak (Zone-I) PWSS | SM/15462 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000106/2023-2024 | 3009/TD | 29/11/2023 | 29/11/2023 | Resource Division | 7.95 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Astichak (Zone-I) PWSS | SM/15462 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Astichak Zone-I PWSS at Egra-II Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001048/2023-2024 | 378/TD | 29/01/2024 | 08/02/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Astichak (Zone-I) PWSS | SM/15462 | Augmentation | Quotation Bill for New Service connection at T/W NO-II, ZONE-I Of ASTICHAK W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004671988/QUOT/03/47 DT. 05-04-2024 Application NO- 2004671988 Application type-New connection Consumer Id- 204266732 |  |  | BILL/00502/2024-2025 | BP-2024-25-91 | 24/04/2024 | 24/04/2024 | WBSEDCL | 7.72 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Astichak (Zone-I) PWSS | SM/15462 | Augmentation | Quotation Bill for New Service connection at T/W NO-I, ZONE- I Of ASTICHAK W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, BALIGHAI C.C.C. Ref. Memo No- 2004626968/QUOT/03/1610 DT. 01-03-2024 Application NO- 2004626968 Application type-New connection Consumer Id- 204233764 |  |  | BILL/04882/2023-2024 | C122421523282 | 16/12/2024 | 16/12/2024 | WBSEDCL | 3.73 | 0 | 0 | 0
Total | [13 empty] | 519.29 | 4.94 | 0.95