## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bajkul Water Supply Scheme (Zone-III) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000318/2022-2023 | 598/TD | 17/06/2022 | 07/07/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.72 | 4.71 | 99.9 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000234/2022-2023 | 2612/TD | 02/02/2023 | 02/02/2023 | Resource Division | 210.83 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 2641/TD | 13/10/2023 | 13/10/2023 | Resource Division | 28.85 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well (Mouza- Pora Chingra, JL No. 155) of Augmentation of Bajkul Zone-II Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-II Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-III Water Supply Scheme under Bhagwanpur- II Block of Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for Additional Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-III Water Supply Scheme under Bhagwanpur- II Block of Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000561/2022-2023 | 2244/TD | 29/12/2022 | 07/02/2023 | PRANTIK DRILLING AGENCY | 61.68 | 32.14 | 52.1 | 90
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Repair and renovation and others allied works of Pump House, Boundary Wall for head works (1st. Tube well) site at mouza- Bajkul,J.L- No -156, under Bajkul - III Water Supply Scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/001184/2023-2024 | 724/TD | 28/02/2024 | 08/04/2024 | PARTHA CONSTRUCTION | 10.65 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Sinking of 300 mm x 200 mm dia x 225 mtr. deep tube well by direct rotary rig method for Replacement of 2nd Tube well of Bajkul Zone-III Water Supply Scheme within Bhagwanpur-I & II Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer |  | ORD/001157/2023-2024 | 608/TD | 16/02/2024 | 07/03/2024 | B. K. ENTERPRISE | 17.8 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 600 cum RCC OHR at Bajkul Zone-III PWSS at Bhagwanpur-I & II Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001053/2023-2024 | 383/TD | 29/01/2024 | 08/02/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Quotation Bill for New Service connection at T/W NO-III, ZONE-III Of BAJKUL W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II Ref. Memo No- 2004606772/QUOT/03/426 DT. 19-02-2024 Application NO- 2004606772 Application type-New connection Reference Id- 204221105 |  |  | BILL/04141/2023-2024 | BP-2023-24-760 | 01/03/2024 | 01/03/2024 | WBSEDCL | 2.86 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Payment of wayleave facility charges (SER-KGP-2024-WL-45) |  |  | BILL/00133/2024-2025 | BP-2024-25-76 | 29/04/2024 | 29/04/2024 | FA & CAO, S.E. RAILWAY, GRC. | 5.41 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Quotation money for shifting of 11 KV OH Henria Feeder at Najir Bazar for Bajukl Zone-III PWSS under Tamluk Division, PHE Dte. |  |  | BILL/01685/2023-2024 | BP-2023-24-743 | 04/01/2024 | 04/01/2024 | WBSEDCL | 2.63 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Quotation Bill for New Service connection at T/W NO-IV, ZONE-III Of BAJKUL W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II Ref. Memo No- 2004606750/QUOT/03/424 DT. 19-02-2024 Application NO- 2004606750 Application type-New connection Reference Id- 204221087 |  |  | BILL/04140/2023-2024 | BP-2023-24-761 | 01/03/2024 | 01/03/2024 | WBSEDCL | 2.62 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III, Block Bhagawanpur II, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000081/2023-2024 | 1275/W/MMD | 04/05/2023 | 31/10/2023 | MENAKA ENTERPRISE | 37.71 | 22.94 | 60.85 | 76
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Laying of Left-Out portion uPVC Pipe line due to uncovered area under Bajkul Zone-III Water Supply Scheme and its adjoining mouzas at different Nodal Point in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000240/2024-2025 | 2679/TD | 22/08/2024 | 29/01/2025 | SWARUPANANDA DAS | 83.59 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk and replacement Tube well at BAJKUL zone III Water supply scheme, BHAGWANPUR - II block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002722/2023-2024 | 1067/W/MMD | 14/03/2024 | 09/03/2025 | DEBJYOTI BASU | 25.9 | 0 | 0 | 55
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Pump House, Boundary Wall and others allied works for 4th Tube well site at moza- Bajkul,J.L- No -156, under Bajkul - III Water Supply scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001248/2023-2024 | 1076/TD | 16/03/2024 | 23/09/2025 | M/S. S. A. CONSTRUCTION | 11.22 | 0 | 0 | 90
16 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Repair and renovation and others allied works of Pump House, Boundary Wall for 2nd. Tube well site at mouza- Bajkul,J.L- No -156, under Bajkul - III Water Supply Scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001246/2023-2024 | 1077/TD | 16/03/2024 | 27/08/2025 | M/S. S. A. CONSTRUCTION | 9.84 | 0 | 0 | 100
17 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Pump House, Boundary Wall and others allied works for 3rd Tube well site at moza- Bajkul,J.L- No -156, under Bajkul - III Water Supply scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000198/2024-2025 | 2322/TD | 23/07/2024 | 08/06/2025 | M/S S M H CONSTRUCTION | 10.68 | 0 | 0 | 100
18 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Supply of documents for way leave permission of Railway Track Between DESHPRAN-HENRIA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Bajkul Zone-III Piped Water Supply Scheme in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. | Assistant Engineer | Junior Engineer | ORD/000148/2024-2025 | 1730/CSD | 20/06/2024 | 10/07/2024 | BIBEKANANDA DAS | 1.16 | 0 | 0 | 100
19 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Jack Pushing of Railway Track from station deshpran and henria of augmentation of Bajkul Zone-III piped Water Supply Scheme of 600 mm dia ms casing pipe and 150 mm dia ms carrier pipe in between mast no 29/18 to mast no 29/19 with in Contai Sub Division under Tamluk Division PHE Dte. (total length =53 m) (nodal point 508 to nodal point 525) | Assistant Engineer | Junior Engineer | ORD/000119/2024-2025 | 1915/TD | 07/06/2024 | 01/01/2025 | ROY CONSTRUCTION | 61.73 | 0 | 0 | 100
20 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Laying of Distribution pipe line to accommodate FHTC (4683 Nos) with construction of R.C.C. Elevated Reservoir of capacity 400 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works for Augmentation of Bajkul Zone - III Water Supply Scheme within Bhagabanpur- I &II Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000540/2023-2024 | 1887/TD | 09/08/2023 | 25/06/2026 | DAS ENTERPRISE | 779.24 | 266.54 | 34.21 | 50
Total | [13 empty] | 1370.07 | 327.29 | 23.89