## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bajkul Water Supply Scheme (Zone-III) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000318/2022-2023 | 598/TD | 17/06/2022 | 07/07/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.72 | 4.71 | 99.9 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000234/2022-2023 | 2612/TD | 02/02/2023 | 02/02/2023 | Resource Division | 210.83 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 2641/TD | 13/10/2023 | 13/10/2023 | Resource Division | 28.85 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well (Mouza- Pora Chingra, JL No. 155) of Augmentation of Bajkul Zone-II Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-II Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-III Water Supply Scheme under Bhagwanpur- II Block of Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for Additional Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-III Water Supply Scheme under Bhagwanpur- II Block of Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000561/2022-2023 | 2244/TD | 29/12/2022 | 07/02/2023 | PRANTIK DRILLING AGENCY | 61.68 | 32.14 | 52.1 | 90
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Repair and renovation and others allied works of Pump House, Boundary Wall for head works (1st. Tube well) site at mouza- Bajkul,J.L- No -156, under Bajkul - III Water Supply Scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/001184/2023-2024 | 724/TD | 28/02/2024 | 08/04/2024 | PARTHA CONSTRUCTION | 10.65 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Sinking of 300 mm x 200 mm dia x 225 mtr. deep tube well by direct rotary rig method for Replacement of 2nd Tube well of Bajkul Zone-III Water Supply Scheme within Bhagwanpur-I & II Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer |  | ORD/001157/2023-2024 | 608/TD | 16/02/2024 | 07/03/2024 | B. K. ENTERPRISE | 17.8 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 600 cum RCC OHR at Bajkul Zone-III PWSS at Bhagwanpur-I & II Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001053/2023-2024 | 383/TD | 29/01/2024 | 08/02/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Quotation Bill for New Service connection at T/W NO-III, ZONE-III Of BAJKUL W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II Ref. Memo No- 2004606772/QUOT/03/426 DT. 19-02-2024 Application NO- 2004606772 Application type-New connection Reference Id- 204221105 |  |  | BILL/04141/2023-2024 | BP-2023-24-760 | 01/03/2024 | 01/03/2024 | WBSEDCL | 2.86 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Payment of wayleave facility charges (SER-KGP-2024-WL-45) |  |  | BILL/00133/2024-2025 | BP-2024-25-76 | 29/04/2024 | 29/04/2024 | FA & CAO, S.E. RAILWAY, GRC. | 5.41 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Quotation money for shifting of 11 KV OH Henria Feeder at Najir Bazar for Bajukl Zone-III PWSS under Tamluk Division, PHE Dte. |  |  | BILL/01685/2023-2024 | BP-2023-24-743 | 04/01/2024 | 04/01/2024 | WBSEDCL | 2.63 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Quotation Bill for New Service connection at T/W NO-IV, ZONE-III Of BAJKUL W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II Ref. Memo No- 2004606750/QUOT/03/424 DT. 19-02-2024 Application NO- 2004606750 Application type-New connection Reference Id- 204221087 |  |  | BILL/04140/2023-2024 | BP-2023-24-761 | 01/03/2024 | 01/03/2024 | WBSEDCL | 2.62 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III, Block Bhagawanpur II, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000081/2023-2024 | 1275/W/MMD | 04/05/2023 | 31/10/2023 | MENAKA ENTERPRISE | 37.71 | 22.94 | 60.85 | 76
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Laying of Left-Out portion uPVC Pipe line due to uncovered area under Bajkul Zone-III Water Supply Scheme and its adjoining mouzas at different Nodal Point in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000240/2024-2025 | 2679/TD | 22/08/2024 | 29/01/2025 | SWARUPANANDA DAS | 83.59 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk and replacement Tube well at BAJKUL zone III Water supply scheme, BHAGWANPUR - II block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002722/2023-2024 | 1067/W/MMD | 14/03/2024 | 09/03/2025 | DEBJYOTI BASU | 25.9 | 0 | 0 | 55
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Pump House, Boundary Wall and others allied works for 4th Tube well site at moza- Bajkul,J.L- No -156, under Bajkul - III Water Supply scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001248/2023-2024 | 1076/TD | 16/03/2024 | 14/08/2025 | M/S. S. A. CONSTRUCTION | 11.22 | 0 | 0 | 90
16 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Repair and renovation and others allied works of Pump House, Boundary Wall for 2nd. Tube well site at mouza- Bajkul,J.L- No -156, under Bajkul - III Water Supply Scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001246/2023-2024 | 1077/TD | 16/03/2024 | 27/08/2025 | M/S. S. A. CONSTRUCTION | 9.84 | 0 | 0 | 100
17 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Pump House, Boundary Wall and others allied works for 3rd Tube well site at moza- Bajkul,J.L- No -156, under Bajkul - III Water Supply scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000198/2024-2025 | 2322/TD | 23/07/2024 | 08/06/2025 | M/S S M H CONSTRUCTION | 10.68 | 0 | 0 | 100
18 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Supply of documents for way leave permission of Railway Track Between DESHPRAN-HENRIA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Bajkul Zone-III Piped Water Supply Scheme in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. | Assistant Engineer | Junior Engineer | ORD/000148/2024-2025 | 1730/CSD | 20/06/2024 | 10/07/2024 | BIBEKANANDA DAS | 1.16 | 0 | 0 | 100
19 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III | SM/15510 | Augmentation | Jack Pushing of Railway Track from station deshpran and henria of augmentation of Bajkul Zone-III piped Water Supply Scheme of 600 mm dia ms casing pipe and 150 mm dia ms carrier pipe in between mast no 29/18 to mast no 29/19 with in Contai Sub Division under Tamluk Division PHE Dte. (total length =53 m) (nodal point 508 to nodal point 525) | Assistant Engineer | Junior Engineer | ORD/000119/2024-2025 | 1915/TD | 07/06/2024 | 01/01/2025 | ROY CONSTRUCTION | 61.73 | 0 | 0 | 100
Total | [13 empty] | 590.82 | 60.75 | 10.28