## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Mahisadal | Central Drilling | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | : Providing drilling crew and other allied works for construction of Tube Well ( 200mm X150mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Amrit Berya W/S Scheme (T/W-II) , Mahisadal Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000181/2023-2024 | 58/CDD | 06/04/2023 | 06/05/2023 | MENAKA ENTERPRISE | 16.22 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Material Requisition To Resource Division |  |  | RTOR000331/2022-2023 | 2984/TD | 27/02/2023 | 27/02/2023 | Resource Division | 27.61 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 450 cum RCC OHR at Amritberya PWSS at Mahisadal Block under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/001043/2023-2024 | 373/TD | 29/01/2024 | 08/02/2024 | ASTER CONSULTANCY | 0.95 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Material Requisition To Resource Division |  |  | RTOR000113/2023-2024 | 77/TD | 05/01/2024 | 05/01/2024 | Resource Division | 21.19 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Quotation of new service connection at Amritberiya w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (App No. 2004714253, Ref ID 204295221) |  |  | BILL/01142/2024-2025 | BP-2024-25-243 | 06/06/2024 | 06/06/2024 | WBSEDCL | 4.8 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Quotation for new service connection at Amritbera w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. (App No. 2004760250, Ref ID 204322037) |  |  | BILL/01334/2024-2025 | BP-2024-25-362 | 01/07/2024 | 01/07/2024 | WBSEDCL | 5.48 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AMRITBERYA and ADJOINING MOUJAS, Block - Mahishadal, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000086/2023-2024 | 1270/W/MMD | 04/05/2023 | 31/10/2023 | MENAKA ENTERPRISE | 27.04 | 21.2 | 78.43 | 60
8 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Ground water based Amritberya Water Supply Scheme by providing Sinking of Tube well, Construction of Pump House, Boundary Wall, Sub-soil Investigation, Construction of OHR (450 cum), Laying Rising main, Laying of Distribution pipe line, FHTC work and 'Operation & Maintenance' within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000500/2023-2024 | 1688/TD | 26/07/2023 | 28/02/2025 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 580.82 | 341.56 | 58.81 | 40
9 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Continuation work order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2025 to 31/12/2025. (12 Months) | Assistant Engineer | Junior Engineer | ORD/000564/2024-2025 | 1285/HSD, | 27/12/2024 | 27/12/2025 | SANTANU PATTANAYAK | 1.5 | 1.2 | 80.09 | 40
10 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Supply and delivery of 3 nos Chairs (with arm rest), 11 nos Chairs (without arm rest) and 1 nos stainless steel Rack (72inch X 36inch X 15 inch with 5 selves) (all articles should be of Godrej Interio Brand) under Office of the Assistant Engineer, Haldia Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001013/2023-2024 | 689/HSD, | 31/01/2024 | 08/01/2025 | MALLIK TRADERS | 0.97 | 0 | 0 | 100
11 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XII) Name of sites: - i) Madhya Hingli PWSS's 1st Tube well Site, 2nd Tube well site, ii) Baksichak PWSS's 1st Tube well Site, iii) Mayachar 1st Tube well Site and 2nd Tube well site. |  | Junior Engineer | ORD/000394/2024-2025 | 1077/HSD, | 05/11/2024 | 12/11/2024 | SANTANU PATTANAYAK | 0.83 | 0 | 0 | 100
12 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XIII) Name of sites: - i) Lakshya PWSS¿s 1st Tube well Site, 2nd Tube well site, 3rd Tube well site ii) Keshabpur jalpai PWSS's 1st Tube well Site, 2nd Tube well Site. |  | Junior Engineer | ORD/000395/2024-2025 | 1078/HSD, | 05/11/2024 | 12/11/2024 | SANTANU PATTANAYAK | 0.83 | 0.83 | 99.94 | 100
13 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XVI) Name of sites: - i) Manoharpur PWSS¿s 1st Tube well site and 2nd Tube well Site. ii) Solat PWSS's 1st Tube well site and 2nd Tube well site, iii) Dakshinchak PWSS's 1st Tube well site. |  | Junior Engineer | ORD/000398/2024-2025 | 1081/HSD, | 05/11/2024 | 12/11/2024 | SANTANU PATTANAYAK | 0.83 | 0.83 | 99.94 | 100
14 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XVII) Name of sites: - i) Dakshinchak (Z-I) PWSS's 2nd Tube well Site, and 3rd Tube well site, ii) Dakshinchak (Z-II) PWSS's 1st Tube well Site (iii) Barsundara PWSS 1st Tube well site and 2nd Tube well site. |  | Junior Engineer | ORD/000399/2024-2025 | 1082/HSD, | 05/11/2024 | 12/11/2024 | SANTANU PATTANAYAK | 0.83 | 0.83 | 99.94 | 100
15 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 3 Nos. Display Board regarding Har-Ggar-Jal (HGJ) of different villages within different PWSS Jurisdiction under Haldia Sub-Division of Tamluk Division, PHE Dte. (H.G.J. Phase-4) Location:- 1) Asathtalya of Asataliya G.P. within Asathtalya PWSS, 2) Barotala of Asataliya G.P. within Asathtalya PWSS, 3) Gopalpur of Kismat Naikundi G.P. within Gopalpur PWSS. | Assistant Engineer | Junior Engineer | ORD/000524/2024-2025 | 23/HSD, | 09/01/2025 | 19/01/2025 | G. S. A. CONSTRUCTION | 0.62 | 0 | 0 | 100
16 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XIV) Name of sites: - i) Bar Sundara PWSS's 3rd Tube well Site, ii) Simulberya PWSS's 1st Tube well site iii) Natshal Lakshya (Z-II) PWSS's 2nd Tube well Site and 3rd Tube well site. iv) Kesabpur Jalpai PWSS's 3rd Tube well site. |  | Junior Engineer | ORD/000396/2024-2025 | 1079/HSD, | 05/11/2024 | 12/11/2024 | SANTANU PATTANAYAK | 0.83 | 0 | 0 | 100
17 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XVIII) Name of sites:- i) Gholpukuria PWSS's (Z-1) 1st Tube well Site, 2nd Tube well site, 3rd Tube well site, ii) Gholpukuria PWSS's (Z-II) PWSS's 1st Tube well Site, 2nd Tube well Site. |  | Junior Engineer | ORD/000402/2024-2025 | 1083/HSD, | 05/11/2024 | 01/01/2025 | G. S. A. CONSTRUCTION | 0.83 | 0 | 0 | 100
18 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 3 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XIX) Name of sites: - i) Jalpai Part -II PWSS's 1st Tube well Site, 2nd Tube well Site and 3rd Tube well Site. |  | Junior Engineer | ORD/000403/2024-2025 | 1084/HSD, | 05/11/2024 | 01/01/2025 | G. S. A. CONSTRUCTION | 0.5 | 0 | 0 | 100
19 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XXI) Name of sites: - i) Tajpur PWSS's 3rd Tube well Site ii) Mahammadpur PWSS's 1st Tube well Site, 2nd Tube well Site iii) Sonachura PWSS 1st Tube well Site and 2nd Tube well site. |  | Junior Engineer | ORD/000405/2024-2025 | 1086/HSD | 05/11/2024 | 01/01/2025 | G. S. A. CONSTRUCTION | 0.83 | 0 | 0 | 100
20 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-VII). Name of sites:- i) Gopalpur PWSS's 4th Tube well Site, ii) Rangibasan PWSS's 1st Tube well Site, 2nd Tube well Site and 3rd Tube well Site. iii) Betkundu PWSS 1st Tube well site. |  | Junior Engineer | ORD/000389/2024-2025 | 1072/HSD, | 05/11/2024 | 12/11/2024 | SANTANU PATTANAYAK | 0.83 | 0 | 0 | 100
21 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-VIII). Name of sites:- i) Betkundu PWSS's 2nd Tube well Site, and 3rd Tube well site, ii) Rajarampur PWSS's 1st Tube well Site and 2nd Tube well Site iii) Natshal Lakshya (Z-I) 1st Tube well Site. |  | Junior Engineer | ORD/000390/2024-2025 | 1073/HSD, | 05/11/2024 | 12/11/2024 | SANTANU PATTANAYAK | 0.83 | 0 | 0 | 100
22 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-IX). Name of sites: - i) Natshal Lakshya (Z-1) PWSS's 2nd Tube well Site, 3rd Tube well site, 4th Tube well site, 5th Tube well site ii) Natshal Lakshya (Z-II) PWSS's 1st Tube well Site. |  | Junior Engineer | ORD/000391/2024-2025 | 1074/HSD, | 05/11/2024 | 01/01/2025 | SANTANU PATTANAYAK | 0.83 | 0 | 0 | 100
23 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XX) Name of sites:- i) Manikpur PWSS's 1st Tube well Site, 2nd Tube well site, 3rd Tube well site, ii) Tajpur PWSS's 1st Tube well Site and 2nd Tube well Site. |  | Junior Engineer | ORD/000404/2024-2025 | 1085/HSD, | 05/11/2024 | 01/01/2025 | G. S. A. CONSTRUCTION | 0.83 | 0 | 0 | 100
24 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 4 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XXII) Name of sites: - i) Solat Headwork site. ii) Chaitanyapur (Zone-II) 2nd Tube well site, 3rd Tube well site and 4th Tube well site. |  | Junior Engineer | ORD/000406/2024-2025 | 1087/HSD, | 05/11/2024 | 01/01/2025 | G. S. A. CONSTRUCTION | 0.67 | 0 | 0 | 100
25 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Box Culvert at HW site & Construction of Retaining wall of ground water based Amritberia Water Supply Scheme within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/001242/2023-2024 | 1082/TD | 16/03/2024 | 01/03/2025 | G. S. CONSTRUCTION | 10.83 | 0 | 0 | 100
26 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 4 Nos. Display Board regarding Har-Ggar-Jal (HGJ) of different villages within different PWSS Jurisdiction under Haldia Sub-Division of Tamluk Division, PHE Dte. (H.G.J. Phase-2) Location:- 1) Anantapur of Asadtalia G.P. within Asathalia PWSS, 2) Jamalchak of Asadtalia G.P. within Asadtalia PWSS, 3) Dakshin Gobindapur of Asadtalia G.P. within Asadtalia PWSS, 4) Dundipur of Horkhali G.P. within Begunberya PWSS. | Assistant Engineer | Junior Engineer | ORD/000522/2024-2025 | 21/HSD | 09/01/2025 | 19/01/2025 | SINGHA ENTERPRISE | 0.83 | 0 | 0 | 100
27 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 4 Nos. Display Board regarding Har-Ggar-Jal (HGJ) of different villages within different PWSS Jurisdiction under Haldia Sub-Division of Tamluk Division, PHE Dte. (H.G.J. Phase-3) Location:- 1) Finga of Horkhali G.P. within Begunberia PWSS, 2) Ataphala of Horkhali G.P. within Begunberia PWSS, 3) Horkhali of Horkhali G.P. within Begunberia PWSS, 4) Begunbere of Horkhali G.P. within Begunberya PWSS. | Assistant Engineer | Junior Engineer | ORD/000523/2024-2025 | 22/HSD, | 09/01/2025 | 19/01/2025 | SNEHASIS BERA | 0.83 | 0 | 0 | 100
28 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 4 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XXIII) Name of sites:- i) Nandigram PWSS 1st Tube well site and 2nd Tube well site. ii) Reyapara PWSS 1st Tube well site and 2nd Tube well site. |  | Junior Engineer | ORD/000408/2024-2025 | 1088/HSD | 05/11/2024 | 01/01/2025 | SANTANU PATTANAYAK | 0.67 | 0.67 | 99.94 | 100
29 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-III) Name of sites: i) Chaitanyapur (Z-I) PWSS's 3rd Tube well site. ii) Chaitanyapur (Z-II) PWSS's 3rd Tube well site, iii) Asadtalia PWSS's, 1st Tube well Site, and 2nd Tube well site and 3rd Tube well site. |  | Junior Engineer | ORD/000426/2024-2025 | 1110/HSD, | 13/11/2024 | 01/01/2025 | SINGHA ENTERPRISE | 0.83 | 0 | 0 | 100
30 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-X) Name of sites:- i) Baramrit Bere PWSS's 1st Tube well Site, 2nd Tube well site, ii) Amritberya PWSS 1st Tube well Site, 2nd Tube well Site iii) Bamanpur 1st Tube well Site. |  | Junior Engineer | ORD/000392/2024-2025 | 1075/HSD, | 05/11/2024 | 12/11/2024 | SANTANU PATTANAYAK | 0.83 | 0 | 0 | 100
31 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XI) Name of sites:- i) Bamanpur PWSS's 1st Tube well Site, ii) Kanchanpur PWSS's 1st Tube well Site, 2nd Tube well Site iii) Sarberya 1st Tube well Site and 2nd Tube well Site. |  | Junior Engineer | ORD/000393/2024-2025 | 1076/HSD, | 05/11/2024 | 12/11/2024 | SANTANU PATTANAYAK | 0.83 | 0 | 0 | 100
32 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XV) Name of sites:- i) Dwariberia PWSS's 1st Tube well Site, and 2nd Tube well site, ii) Barbasudevpur PWSS's 1st Tube well Site, 2nd Tube well Site and 3rd Tube well Site. |  | Junior Engineer | ORD/000397/2024-2025 | 1080/HSD, | 05/11/2024 | 12/11/2024 | SANTANU PATTANAYAK | 0.83 | 0.83 | 99.94 | 100
33 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-I) Name of sites- i) Dhenuka PWSS's Head Work Site and 2nd Tube well Site. ii) Tabakhali PWSS's Head Work site and 3rd Tube well site, iii) Begunberia PWSS's, Head Work site. |  | Junior Engineer | ORD/000424/2024-2025 | 1108/HSD, | 13/11/2024 | 01/01/2025 | SINGHA ENTERPRISE | 0.83 | 0 | 0 | 100
34 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-II) Name of sites: i) Begunberia PWSS's, 2nd Tube well site and 3rd Tube well site, ii) Chaitanyapur PWSS (Zone-I)'s 1st Tube well Site, 2nd Tube well site and 3rd Tube well site. |  | Junior Engineer | ORD/000425/2024-2025 | 1109/HSD, | 13/11/2024 | 01/01/2025 | SINGHA ENTERPRISE | 0.83 | 0 | 0 | 100
35 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-IV) Name of sites: - i) Urddhabmal PWSS¿s 1st Tube well Site, 2nd Tube well site, ii) Jaynagar PWSS's 1st Tube well Site, 2nd Tube well Site iii) Erakhali PWSS 1st Tube well site. |  | Junior Engineer | ORD/000427/2024-2025 | 1111/HSD, | 13/11/2024 | 01/01/2025 | SINGHA ENTERPRISE | 0.83 | 0 | 0 | 100
36 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-V) Name of sites: - i) Erakhali PWSS¿s 2nd Tube well Site, ii) Mohanpur PWSS's 1st Tube well Site, 2nd Tube well Site iii) Hariballbhpur PWSS 1st Tube well Site, 2nd Tube well site. |  | Junior Engineer | ORD/000428/2024-2025 | 1112/HSD, | 13/11/2024 | 01/01/2025 | SINGHA ENTERPRISE | 0.83 | 0 | 0 | 100
37 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-VI) Name of sites:- i) Kapaseria PWSS's 1st Tube well Site, 2nd Tube well site, ii) Gopalpur PWSS's 1st Tube well Site, 2nd Tube well Site and 3rd Tube well Site. |  | Junior Engineer | ORD/000429/2024-2025 | 1113/HSD, | 13/11/2024 | 20/11/2024 | SINGHA ENTERPRISE | 0.83 | 0 | 0 | 100
38 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Installation of 4 Nos. Display Board regarding Har-Ggar-Jal (HGJ) of different villages within different PWSS Jurisdiction under Haldia Sub-Division of Tamluk Division, PHE Dte. (H.G.J. Phase-1) Location:- 1) Dwariberiyarchak of Lakshya - I G.P. within Lakshya PWSS, 2) Rajchak of Natshal - 2 G.P. within Gopalpur PWSS, 3) Ghagra of Kishmat Naikundi G.P. within Rangibasan PWSS, 4) Sarberia of Kishmat Naikundi within Sarberia PWSS. | Assistant Engineer | Junior Engineer | ORD/000520/2024-2025 | 20/HSD, | 09/01/2025 | 19/01/2025 | SANTANU PATTANAYAK | 0.83 | 0 | 0 | 100
Total | [13 empty] | 718.99 | 367.95 | 51.18