## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Mahisadal | Central Drilling | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | : Providing drilling crew and other allied works for construction of Tube Well ( 200mm X150mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Amrit Berya W/S Scheme (T/W-II) , Mahisadal Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000181/2023-2024 | 58/CDD | 06/04/2023 | 06/05/2023 | MENAKA ENTERPRISE | 16.22 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Material Requisition To Resource Division |  |  | RTOR000331/2022-2023 | 2984/TD | 27/02/2023 | 27/02/2023 | Resource Division | 27.61 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 450 cum RCC OHR at Amritberya PWSS at Mahisadal Block under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/001043/2023-2024 | 373/TD | 29/01/2024 | 08/02/2024 | ASTER CONSULTANCY | 0.95 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Material Requisition To Resource Division |  |  | RTOR000113/2023-2024 | 77/TD | 05/01/2024 | 05/01/2024 | Resource Division | 21.19 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Quotation of new service connection at Amritberiya w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (App No. 2004714253, Ref ID 204295221) |  |  | BILL/01142/2024-2025 | BP-2024-25-243 | 06/06/2024 | 06/06/2024 | WBSEDCL | 4.8 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Quotation for new service connection at Amritbera w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. (App No. 2004760250, Ref ID 204322037) |  |  | BILL/01334/2024-2025 | BP-2024-25-362 | 01/07/2024 | 01/07/2024 | WBSEDCL | 5.48 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AMRITBERYA and ADJOINING MOUJAS, Block - Mahishadal, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000086/2023-2024 | 1270/W/MMD | 04/05/2023 | 31/10/2023 | MENAKA ENTERPRISE | 27.04 | 21.2 | 78.43 | 60
8 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Ground water based Amritberya Water Supply Scheme by providing Sinking of Tube well, Construction of Pump House, Boundary Wall, Sub-soil Investigation, Construction of OHR (450 cum), Laying Rising main, Laying of Distribution pipe line, FHTC work and 'Operation & Maintenance' within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000500/2023-2024 | 1688/TD | 26/07/2023 | 28/02/2025 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 580.82 | 341.56 | 58.81 | 40
9 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 10/09/2024 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 0 | 100
10 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | AMRITBERYA AND ADJOINING MOUJAS | SM/15511 | New | Continuation work order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2025 to 31/12/2025. (12 Months) | Assistant Engineer | Junior Engineer | ORD/000564/2024-2025 | 1285/HSD, | 27/12/2024 | 27/12/2025 | SANTANU PATTANAYAK | 1.5 | 1.2 | 80.09 | 40
Total | [13 empty] | 696.02 | 363.96 | 52.29