## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | CHAK BHABANI & ADJOINING MOUJAS PWSS | SM/15512 | New | Sinking of Tube well,Pump House ,Construction of 350 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2843 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Chakbhabani PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000489/2023-2024 | 1564/TD | 19/07/2023 | 15/01/2024 | TARUN KOLEY | 947.78 | 606.52 | 63.99 | 35
2 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | CHAK BHABANI & ADJOINING MOUJAS PWSS | SM/15512 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHAK BHABANI & ADJOINING MOUJAS PWSS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001712/2022-2023 | 629/W/MMD | 20/03/2023 | 07/03/2025 | ALPHA ENTERPRISE | 25.24 | 23.52 | 93.2 | 100
3 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | CHAK BHABANI & ADJOINING MOUJAS PWSS | SM/15512 | New | Material Requisition To Resource Division |  |  | RTOR000343/2022-2023 | 2996/TD | 27/02/2023 | 27/02/2023 | Resource Division | 22.46 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | CHAK BHABANI & ADJOINING MOUJAS PWSS | SM/15512 | New | Chakbhabani W/S scheme PH-II Application no.-2004520828 ref.-204155254 |  |  | BILL/03191/2023-2024 | BP-2023-24-483 | 27/12/2023 | 27/12/2023 | WBSEDCL | 3.58 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | CHAK BHABANI & ADJOINING MOUJAS PWSS | SM/15512 | New | Chakbhabani W/S scheme PH-I Application no.-2004520839 ref.-204155241 |  |  | BILL/03190/2023-2024 | BP-2023-24-484 | 27/12/2023 | 27/12/2023 | WBSEDCL | 3.91 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | CHAK BHABANI & ADJOINING MOUJAS PWSS | SM/15512 | New | Material Requisition To Resource Division |  |  | RTOR000023/2024-2025 | 1649/TD | 29/04/2024 | 29/04/2024 | Resource Division | 17.51 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | CHAK BHABANI & ADJOINING MOUJAS PWSS | SM/15512 | New | Additional Quotation Bill of Erection for the Service connection at T/W NO-II Of CHAKBHABANI W/S Scheme Under Jal Jeevan Mission under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASHPUR C.C.C. Ref. Memo No-PTP/QOT/HT/151 DT. 14-05-2024 Application NO- 100000107893 DT. 14-05-2024 Application type-ADDITIONAL QUOTATION FOR SERVICE CONNECTION REF. Id- 860299943 |  |  | BILL/01129/2024-2025 | BP-2024-25-245 | 06/06/2024 | 06/06/2024 | WBSEDCL | 0.37 | 0 | 0 | 0
Total | [13 empty] | 1020.85 | 630.04 | 61.72