## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | DUBDA IT'S ADJOINING MOUJAS PWSS | SM/15513 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DUBDA and ADJOINING MOUJAS, Block Egra II, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000087/2023-2024 | 1269/W/MMD | 04/05/2023 | 31/10/2023 | MENAKA ENTERPRISE | 27.04 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-II | Tamluk Division | DUBDA IT'S ADJOINING MOUJAS PWSS | SM/15513 | New | Material Requisition To Resource Division |  |  | RTOR000320/2022-2023 | 2974/TD | 27/02/2023 | 27/02/2023 | Resource Division | 49.63 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Egra-II | Tamluk Division | DUBDA IT'S ADJOINING MOUJAS PWSS | SM/15513 | New | Sinking of Tube Well ,Rising main ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , OHR (Intze type with pile foundation) & Accommodate FHTC (5135 nos) Including 2 Years of Operation & Maintenance under JJM with allied work for Dubda & Khagda PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000511/2023-2024 | 1733/TD | 31/07/2023 | 27/10/2025 | MAHAVIR PUMPS MFG. PVT. LTD. | 1235.52 | 236.48 | 19.14 | 48
Total | [13 empty] | 1312.19 | 236.48 | 18.02