## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | DUBDA IT'S ADJOINING MOUJAS PWSS | SM/15513 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DUBDA and ADJOINING MOUJAS, Block Egra II, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000087/2023-2024 | 1269/W/MMD | 04/05/2023 | 31/10/2023 | MENAKA ENTERPRISE | 27.04 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-II | Central Drilling | DUBDA IT'S ADJOINING MOUJAS PWSS | SM/15513 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3 | PURBA MEDINIPUR | Egra-II | Tamluk Division | DUBDA IT'S ADJOINING MOUJAS PWSS | SM/15513 | New | Sinking of Tube Well ,Rising main ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , OHR (Intze type with pile foundation) & Accommodate FHTC (5135 nos) Including 2 Years of Operation & Maintenance under JJM with allied work for Dubda & Khagda PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000511/2023-2024 | 1733/TD | 31/07/2023 | 25/04/2026 | MAHAVIR PUMPS MFG. PVT. LTD. | 1235.52 | 236.48 | 19.14 | 48
4 | PURBA MEDINIPUR | Egra-II | Tamluk Division | DUBDA IT'S ADJOINING MOUJAS PWSS | SM/15513 | New | Material Requisition To Resource Division |  |  | RTOR000320/2022-2023 | 2974/TD | 27/02/2023 | 27/02/2023 | Resource Division | 49.63 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | DUBDA IT'S ADJOINING MOUJAS PWSS | SM/15513 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 10/09/2024 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 0 | 100
6 | PURBA MEDINIPUR | Egra-II | Tamluk Division | DUBDA IT'S ADJOINING MOUJAS PWSS | SM/15513 | New | Material Requisition To Resource Division |  |  | RTOR000024/2025-2026 | 2093/TD | 12/08/2025 | 12/08/2025 | Resource Division | 25.05 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | DUBDA IT'S ADJOINING MOUJAS PWSS | SM/15513 | New | Quotation Bill for New Service connection at T/W NO-II Of DUBDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2005020296/QUOT/03 DT. 23-12-2024 Application NO- 2005020296 Application type-New connection Consumer Id- 204480414 |  |  | BILL/03946/2024-2025 | C012553116780 | 31/01/2025 | 31/01/2025 | WBSEDCL | 4.24 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | DUBDA IT'S ADJOINING MOUJAS PWSS | SM/15513 | New | Quotation Bill for New Service connection at T/W NO-I Of DUBDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2005050848/QUOT/03/962 DT. 20-01-2025 Application NO- 2005050848 Application type-New connection Consumer Id- 204501203 |  |  | BILL/04272/2024-2025 | C032554781201 | 17/03/2025 | 17/03/2025 | WBSEDCL | 19.21 | 0 | 0 | 0
Total | [13 empty] | 22710.87 | 236.48 | 1.04