## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | AILAN AND IT'S ADJOINING MOUJAS PWSS | SM/15514 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AILAN and ADJOINING MOUJAS, Block - Egra I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000088/2023-2024 | 1268/W/MMD | 04/05/2023 | 31/10/2023 | MENAKA ENTERPRISE | 27.04 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-I | Tamluk Division | AILAN AND IT'S ADJOINING MOUJAS PWSS | SM/15514 | New | Material Requisition To Resource Division |  |  | RTOR000131/2022-2023 | 2415/TD | 16/01/2023 | 16/01/2023 | Resource Division | 25.14 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Egra-I | Tamluk Division | AILAN AND IT'S ADJOINING MOUJAS PWSS | SM/15514 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 450 cum RCC OHR at Ailan PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000186/2024-2025 | 2196/TD | 09/07/2024 | 19/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
4 | PURBA MEDINIPUR | Egra-I | Tamluk Division | AILAN AND IT'S ADJOINING MOUJAS PWSS | SM/15514 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 0 | 0 | 51
5 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | AILAN AND IT'S ADJOINING MOUJAS PWSS | SM/15514 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 10/09/2024 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 0 | 100
Total | [13 empty] | 19571.26 | 0 | 0