## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | AILAN AND IT'S ADJOINING MOUJAS PWSS | SM/15514 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AILAN and ADJOINING MOUJAS, Block - Egra I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000088/2023-2024 | 1268/W/MMD | 04/05/2023 | 31/10/2023 | MENAKA ENTERPRISE | 27.04 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-I | Tamluk Division | AILAN AND IT'S ADJOINING MOUJAS PWSS | SM/15514 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 113.64 | 0.58 | 51
3 | PURBA MEDINIPUR | Egra-I | Tamluk Division | AILAN AND IT'S ADJOINING MOUJAS PWSS | SM/15514 | New | Material Requisition To Resource Division |  |  | RTOR000131/2022-2023 | 2415/TD | 16/01/2023 | 16/01/2023 | Resource Division | 25.14 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | AILAN AND IT'S ADJOINING MOUJAS PWSS | SM/15514 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 10/09/2024 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 0 | 100
5 | PURBA MEDINIPUR | Egra-I | Tamluk Division | AILAN AND IT'S ADJOINING MOUJAS PWSS | SM/15514 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 450 cum RCC OHR at Ailan PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000186/2024-2025 | 2196/TD | 09/07/2024 | 19/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
6 | PURBA MEDINIPUR | Egra-I | Tamluk Division | AILAN AND IT'S ADJOINING MOUJAS PWSS | SM/15514 | New | Material Requisition To Resource Division |  |  | RTOR000006/2025-2026 | 2069/TD | 12/08/2025 | 12/08/2025 | Resource Division | 18.76 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | AILAN AND IT'S ADJOINING MOUJAS PWSS | SM/15514 | New | Quotation Bill for New Service connection at T/W NO-I Of AILAN W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2005170629/QUOT/03/175 DT. 16-04-2025 Application NO- 2005170629 Application type-New connection Consumer Id- 204588611 |  |  | BILL/00705/2025-2026 |  | 08/05/2025 | 08/05/2025 | WBSEDCL | 18.41 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | AILAN AND IT'S ADJOINING MOUJAS PWSS | SM/15514 | New | Quotation Bill for New Service connection at T/W NO-II Of AILAN W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2005047686/QUOT/03/131 DT. 27-01-2025 Application NO- 2005047686 Application type-New connection Consumer Id- 204498435 |  |  | BILL/04503/2024-2025 | C032587409521 | 27/03/2025 | 27/03/2025 | WBSEDCL | 3.8 | 0 | 0 | 0
Total | [13 empty] | 19612.23 | 114.59 | 0.58