## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Khejuri-II | Tamluk Division | DEKHALI AND ADJOINING MOUJAS PWSS | SM/15515 | New | Material Requisition To Resource Division |  |  | RTOR000227/2022-2023 | 2707/TD | 06/02/2023 | 06/02/2023 | Resource Division | 20.88 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Khejuri-II | Midnapore Mechanical | DEKHALI AND ADJOINING MOUJAS PWSS | SM/15515 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DEKHALI and ADJOINING MOUJAS, Block ¿ Khejuri II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001590/2022-2023 | 474/W/MMD | 20/03/2023 | 16/09/2023 | KAMAKSHYA ENTERPRISE | 27.04 | 23.1 | 85.45 | 60
3 | PURBA MEDINIPUR | Khejuri-II | Tamluk Division | DEKHALI AND ADJOINING MOUJAS PWSS | SM/15515 | New | Quotation for new service connection at Dekhali w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.(App No. 2004783456, Ref ID 204336497) |  |  | BILL/00590/2024-2025 | BP-2024-25-288 | 29/07/2024 | 29/07/2024 | WBSEDCL | 12.1 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Khejuri-II | Midnapore Mechanical | DEKHALI AND ADJOINING MOUJAS PWSS | SM/15515 | New | Quotation for new service connection at Dekhali w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004640113, Ref ID - 204244140) |  |  | BILL/04492/2023-2024 | BP-2023-24-865 | 16/03/2024 | 16/03/2024 | WBSEDCL | 8.79 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Khejuri-II | Tamluk Division | DEKHALI AND ADJOINING MOUJAS PWSS | SM/15515 | New | Sinking of Tube Well ,Rising main,Head work site pipe connection,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works, with laying distribution system ,Rigid Pavement, Pump House &Boundary Wall, Providing Functional Household Tap Connection (4781 Nos), including 2 years Operation & Maintenance For Halud Bari, Dekhali, Pipe water supply Scheme within Khejuri-II Block, within Contai Sub-Division Under Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000287/2023-2024 | 454/TD | 04/05/2023 | 01/11/2025 | TAPAS SANTRA | 1701.13 | 815.02 | 47.91 | 78
Total | [13 empty] | 1769.94 | 838.12 | 47.35