## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amtalia Accommodate FHTC under Contai-II (Deshapran) Block within Purba Medinipur District. | SM/15635 | Augmentation | Laying of different dia HDPE Pipe line to accommodate remaining FHTC under Augmentation of Amtalia PWSS within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division,PHE Dte., in the District of Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000142/2023-2024 | 285/TD | 20/04/2023 | 30/05/2023 | GHOSH ENTERPRISE | 56.31 | 55.82 | 99.13 | 100
Total | [13 empty] | 56.31 | 55.82 | 99.13