## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III | SM/15841 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme (Zone-III) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000457/2022-2023 | 1856/TD | 21/11/2022 | 11/12/2022 | ASTER CONSULTANCY | 3.46 | 3.22 | 93.13 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III | SM/15841 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 3010/TD | 29/11/2023 | 29/11/2023 | Resource Division | 0.61 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III | SM/15841 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 2083/TD | 28/08/2023 | 28/08/2023 | Resource Division | 13.95 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III | SM/15841 | Augmentation | Drum Sheet walling, road restoration for distribution pipe line ( for FHTC) & Accommodate FHTC (172 Nos) under JJM with allied work for KANPUR (Zone-III) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer |  | ORD/000315/2024-2025 | 3182/TD | 30/09/2024 | 09/11/2024 | MAITY CONSTRUCTION | 91.37 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III | SM/15841 | Augmentation | Quotation Bill for New Service connection at T/W NO-II , zone-III Of KANPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004927974/QUOT/03 DT. 04-10-2024 Application NO- 2004927974 Application type-New connection Consumer Id- 204417444 |  |  | BILL/02973/2024-2025 | BP-2024-25-779 | 05/11/2024 | 05/11/2024 | WBSEDCL | 4.94 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III | SM/15841 | Augmentation | Quotation Bill for New Service connection at T/W NO-I, ZONE-III Of KANPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004927967/QUOT/03 DT. 04-10-2024 Application NO- 2004927967 Application type-New connection Consumer Id- 204417441 |  |  | BILL/02988/2024-2025 | C112422744521 | 18/11/2024 | 18/11/2024 | WBSEDCL | 4.99 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III | SM/15841 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000052/2023-2024 | 1216/W/MMD | 25/04/2023 | 30/09/2025 | BHABANI PRASAD MANNA | 83.38 | 0 | 0 | 34
8 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR ZONE-III | SM/15841 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 99 Nos) under JJM with allied work for KANPUR (Zone-III) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000704/2023-2024 | 2820/TD | 08/11/2023 | 01/04/2025 | BASANTA KUMAR MAITY | 282.99 | 0 | 0 | 55
Total | [13 empty] | 485.7 | 3.22 | 0.66