## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | JHAUGERYA PIPED WATER SUPPLY SCHEME. | SM/15842 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at JHAUGERYA PIPED WATER SUPPLY SCHEME in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000044/2023-2024 | 1215/W/MMD | 25/04/2023 | 30/09/2026 | BHABANI PRASAD MANNA | 12.05 | 0 | 0 | 30
2 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | JHAUGERYA PIPED WATER SUPPLY SCHEME. | SM/15842 | New | Material Requisition To Resource Division |  |  | RTOR000350/2022-2023 | 3016/TD | 27/02/2023 | 27/02/2023 | Resource Division | 15.15 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | JHAUGERYA PIPED WATER SUPPLY SCHEME. | SM/15842 | New | Material Requisition To Resource Division |  |  | RTOR000145/2023-2024 | 124/TD | 05/01/2024 | 05/01/2024 | Resource Division | 0.97 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | JHAUGERYA PIPED WATER SUPPLY SCHEME. | SM/15842 | New | Quotation Bill for New Service connection at T/W NO-I Of JHAUGERIA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004966048/QUOT/03 DT. 22-11-2024 Application NO- 2004966048 Application type-New connection Consumer Id- 204446057 |  |  | BILL/01295/2024-2025 |  | 16/12/2024 | 16/12/2024 | WBSEDCL | 2.54 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | JHAUGERYA PIPED WATER SUPPLY SCHEME. | SM/15842 | New | Quotation Bill for New Service connection at T/W NO-I Of JHAUGERIA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2005019326/QUOT/03 DT. 23-12-2024 Application NO- 2005019326 Application type-New connection Consumer Id- 204480239 |  |  | BILL/01502/2024-2025 |  | 06/03/2025 | 06/03/2025 | WBSEDCL | 2.59 | 0 | 0 | 0
Total | [13 empty] | 33.31 | 0 | 0