## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-II | SM/15843 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 2082/TD | 28/08/2023 | 28/08/2023 | Resource Division | 13.54 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-II | SM/15843 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000108/2023-2024 | 3011/TD | 29/11/2023 | 29/11/2023 | Resource Division | 1.47 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-II | SM/15843 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme under Tamluk Division, PHE Dte. ( PART- II ) | Assistant Engineer | Junior Engineer | ORD/000968/2022-2023 | 1058/TD | 18/08/2022 | 07/09/2022 | ASTER CONSULTANCY | 3.6 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-II | SM/15843 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT ZONE-2, TW-2 OF KANPUR WS SCHEME UNDER MMD PHE DTE,BLOCK-RAMNAGAR-II, DIGHA CCC APPLCATION NO-2004746438, CON ID-204313992 |  |  | BILL/01139/2024-2025 | BP-2024-25-252 | 06/06/2024 | 06/06/2024 | WBSEDCL | 6.19 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-II | SM/15843 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000052/2023-2024 | 1216/W/MMD | 25/04/2023 | 30/09/2025 | BHABANI PRASAD MANNA | 83.38 | 0 | 0 | 34
Total | [13 empty] | 108.18 | 0 | 0