## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-4 | SM/15844 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chirulia Chatla Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000496/2022-2023 | 1932./TD | 28/11/2022 | 18/12/2022 | ASTER CONSULTANCY | 3.46 | 2.89 | 83.71 | 100
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Chirulia-Chatla Zone-4 | SM/15844 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Egra - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000050/2023-2024 | 1207/W/MMD | 25/04/2023 | 31/12/2025 | BHABANI PRASAD MANNA | 59.85 | 0 | 0 | 20
3 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-4 | SM/15844 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 173 Nos) under JJM with allied work for Chirulia-Chatla (Zone-IV) PWSS within Egra-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000523/2023-2024 | 1759/TD | 01/08/2023 | 28/01/2024 | SUSIL KUMAR HAZRA | 262.49 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-4 | SM/15844 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2023-2024 | 2076/TD | 28/08/2023 | 28/08/2023 | Resource Division | 15.05 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-4 | SM/15844 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000093/2023-2024 | 2996/TD | 29/11/2023 | 29/11/2023 | Resource Division | 1.07 | 0 | 0 | 0
Total | [13 empty] | 341.91 | 2.89 | 0.85