## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-IV | SM/15845 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bathuary Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000463/2022-2023 | 1866/TD | 21/11/2022 | 11/12/2022 | ASTER CONSULTANCY | 3.3 | 2.98 | 90.28 | 100
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Bathuari Zone-IV | SM/15845 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at at different PWSS of Block Egra - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000073/2023-2024 | 1242/W/MMD | 28/04/2023 | 31/05/2025 | BHABANI PRASAD MANNA | 84.29 | 0 | 0 | 70
3 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-IV | SM/15845 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (48 nos) under JJM with allied work for Bathuari (Zone-IV) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000526/2023-2024 | 1762/TD | 01/08/2023 | 01/12/2025 | ARABINDA GHOSH | 278.74 | 26.66 | 9.56 | 20
4 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-IV | SM/15845 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 2073/TD | 28/08/2023 | 28/08/2023 | Resource Division | 15.35 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-IV | SM/15845 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000099/2023-2024 | 3002/TD | 29/11/2023 | 29/11/2023 | Resource Division | 0.3 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-IV | SM/15845 | Augmentation | Land Developing at Head Work site & 2nd Tube well site for Augmentation of Bathuary (Zone-IV) Water Supply Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 3069/TD | 19/09/2024 | 09/10/2024 | GHOSH ENTERPRISE | 4.62 | 0 | 0 | 100
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Bathuari Zone-IV | SM/15845 | Augmentation | Quotation Bill for New Service connection at T/W NO-I, ZONE-IV Of BATHUARY W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004714304/QUOT/03/142 DT. 03-05-2024 Application NO- 2004714304 Application type-New connection Consumer Id- 204294967 |  |  | BILL/01278/2024-2025 | BP-2024-25-337 | 25/06/2024 | 25/06/2024 | WBSEDCL | 4.73 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Bathuari Zone-IV | SM/15845 | Augmentation | Quotation Bill for New Service connection at T/W NO-II, ZONE-IV Of BATHUARY W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004941929/QUOT/03/769 DT. 25-10-2024 Application NO- 2004941929 Application type-New connection Consumer Id- 204428742 |  |  | BILL/03020/2024-2025 | C112429746394 | 25/11/2024 | 25/11/2024 | WBSEDCL | 3.67 | 0 | 0 | 0
Total | [13 empty] | 394.99 | 29.63 | 7.5