## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-III | SM/15846 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 2075/TD | 28/08/2023 | 28/08/2023 | Resource Division | 14.02 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-III | SM/15846 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000095/2023-2024 | 2998/TD | 29/11/2023 | 29/11/2023 | Resource Division | 1.64 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-III | SM/15846 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone- III) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000330/2023-2024 | 740/TD | 25/05/2023 | 14/06/2023 | ASTER CONSULTANCY | 3.49 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-III | SM/15846 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Sankarpur Zone-III PWSS at Ramnagar-II Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001044/2023-2024 | 374/TD | 29/01/2024 | 08/02/2024 | ASTER CONSULTANCY | 0.95 | 0 | 0 | 100
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-III | SM/15846 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT ZONE-3, TW-II OF SHANKARPUR WS SCHEME UNDER MMD, PHE DTE, BLOCK-RAMNAGAR -1, DIGHA CCC APP. NO-2004746394 CON ID-204313991 |  |  | BILL/01143/2024-2025 | BP-2024-25-257 | 06/06/2024 | 06/06/2024 | WBSEDCL | 0.71 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-III | SM/15846 | Augmentation | Quotation Bill for New Service connection at T/W NO-I , ZONE-III Of SANKARPUR W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-I, DIGHA C.C.C. Ref. Memo No- 2004626526/QUOT/03 DT. 04-03-2024 Application NO- 2004626526 Application type-New connection Consumer Id- 204233340 |  |  | BILL/04341/2023-2024 | BP-2023-24-809 | 11/03/2024 | 11/03/2024 | WBSEDCL | 3.85 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-III | SM/15846 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments atPiped Water Supply Scheme for Sankarpur Zone-III in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000040/2023-2024 | 1211/W/MMD | 25/04/2023 | 10/11/2027 | S.S.GHORAI | 23.52 | 0 | 0 | 75
8 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-III | SM/15846 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 267 Nos) under JJM with allied work for SANKARPUR (Zone-III) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000519/2023-2024 | 1756/TD | 01/08/2023 | 27/01/2026 | SUSIL KUMAR HAZRA | 193.96 | 0 | 0 | 40
9 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-III | SM/15846 | Augmentation | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 29/08/2024 | S.S.GHORAI | 2.12 | 0 | 0 | 50
10 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-III | SM/15846 | Augmentation | Laying distribution pipe line due to Re-design, & Accommodate Balance FHTC ( 98 Nos) under JJM with allied work for SANKARPUR (Zone-III) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division ,PHED , Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000109/2024-2025 | 1903/TD | 07/06/2024 | 02/07/2024 | SOUMYA ENTERPRISE | 53.79 | 0 | 0 | 65
Total | [13 empty] | 298.05 | 0 | 0