## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-V | SM/15847 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone-V) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000498/2022-2023 | 1934/TD | 28/11/2022 | 18/12/2022 | ASTER CONSULTANCY | 3.46 | 3.3 | 95.54 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-V | SM/15847 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 2069/TD | 28/08/2023 | 28/08/2023 | Resource Division | 14.56 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-V | SM/15847 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 3000/TD | 29/11/2023 | 29/11/2023 | Resource Division | 1.98 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-V | SM/15847 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Sankarpur Zone-V PWSS at Ramnagar - I Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000866/2023-2024 | 189/TD | 10/01/2024 | 20/01/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-V | SM/15847 | Augmentation | Sankarpur W/S scheme TW no.-I, Z-V Ref.-204156069 Application ID-2004521724 |  |  | BILL/03157/2023-2024 | BP-2023-24-443 | 19/12/2023 | 19/12/2023 | WBSEDCL | 3.08 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-V | SM/15847 | Augmentation | Sankarpur W/S scheme T/W-II, Z-V Application-no.-2004522973 Ref.-204157003 |  |  | BILL/03166/2023-2024 | BP-2023-24-444 | 19/12/2023 | 19/12/2023 | WBSEDCL | 3 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-V | SM/15847 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments atPiped Water Supply Scheme for Sankarpur Zone-V in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000042/2023-2024 | 1213/W/MMD | 25/04/2023 | 22/10/2023 | SUBHASIS ROY | 21.6 | 19.98 | 92.49 | 90
8 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-V | SM/15847 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 321 Nos) under JJM with allied work for SANKARPUR (Zone-V) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000507/2023-2024 | 1729/TD | 31/07/2023 | 21/02/2026 | ONKAR ENTERPRISE | 194.4 | 62.64 | 32.22 | 55
9 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-V | SM/15847 | Augmentation | Laying distribution pipe line due to Re- design of pipe line & Accommodate Balance FHTC ( 110 Nos) under JJM with allied work for SANKARPUR (Zone-V) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000254/2024-2025 | 2840/TD | 05/09/2024 | 24/03/2025 | ONKAR ENTERPRISE | 57.51 | 0 | 0 | 100
Total | [13 empty] | 300.54 | 86.87 | 28.91