## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Deshopran | Central Drilling | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS | SM/15848 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 230 mtrs. Depth) by utilising Departmental machineries for Purba Teghari W/S Scheme(TW-III), Deshpran block under Purba Medinipur District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000014/2023-2024 | 12/CDD | 04/04/2023 | 04/05/2023 | MENAKA ENTERPRISE | 13.29 | 0 | 0 | 100
2 | PURBA MEDINIPUR | Deshopran | Central Drilling | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS | SM/15848 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 230 mtrs. Depth) by utilising Departmental machineries for Purba Teghari W/S Scheme(TW-II), Deshpran block under Purba Medinipur District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000015/2023-2024 | 19/CDD | 04/04/2023 | 04/05/2023 | MENAKA ENTERPRISE | 13.29 | 0 | 0 | 100
3 | PURBA MEDINIPUR | Deshopran | Tamluk Division | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS | SM/15848 | New | Material Requisition To Resource Division |  |  | RTOR000349/2022-2023 | 3013/TD | 27/02/2023 | 27/02/2023 | Resource Division | 14.09 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS | SM/15848 | New | Electric Quotation for PURBA TEGHARI, Water Supply Scheme , T/W-II, (Ref. ID-204072721) |  |  | BILL/02537/2023-2024 | BP-2023-24-307 | 01/11/2023 | 01/11/2023 | WBSEDCL | 0.13 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS | SM/15848 | New | Additional Electric Quotiaton for PURBA TEGHARI Water Supply Scheme, T/W- I, (Ref. ID-860281573) |  |  | BILL/02878/2023-2024 | BP-2023-24-339 | 10/11/2023 | 10/11/2023 | WBSEDCL | 2.96 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS | SM/15848 | New | Electric Quotation for PURBA TEGHARI, Water Supply Scheme , T/W-I, (Ref. ID-204072720) |  |  | BILL/02536/2023-2024 | BP-2023-24-308 | 01/11/2023 | 01/11/2023 | WBSEDCL | 0.13 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Deshopran | Tamluk Division | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS | SM/15848 | New | Material Requisition To Resource Division |  |  | RTOR000072/2024-2025 | 2975/TD | 12/09/2024 | 12/09/2024 | Resource Division | 1.4 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Deshopran | Tamluk Division | PURBA TEGHARI & IT'S ADJOINING MOUJAS PWSS | SM/15848 | New | Instalation of display Board at different work site of Purba Teghari & its adjoining Moujas New PWSS in Deshpran Block & Augmentation of Contai Saline Area Zone-I (Phase-A) & Augmentation of Contai Saline Area Zone-I (Phase-B) PWSS in Contai-III Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000565/2024-2025 | 2442/CSD | 22/10/2024 | 29/10/2024 | AMIT PAYRA | 0.62 | 0 | 0 | 100
Total | [13 empty] | 45.91 | 0 | 0