## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | DAHA DAYA PIPED WATER SUPPLY SCHEME. | SM/15849 | New | Material Requisition To Resource Division |  |  | RTOR000271/2022-2023 | 2672/TD | 06/02/2023 | 06/02/2023 | Resource Division | 10.22 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | DAHA DAYA PIPED WATER SUPPLY SCHEME. | SM/15849 | New | Material Requisition To Resource Division |  |  | RTOR000125/2023-2024 | 93//TD | 05/01/2024 | 05/01/2024 | Resource Division | 1.66 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | DAHA DAYA PIPED WATER SUPPLY SCHEME. | SM/15849 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at DAHA DAYA PIPED WATER SUPPLY SCHEME in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000043/2023-2024 | 1214/W/MMD | 25/04/2023 | 30/09/2025 | THE GODFATHER TRADING COMPANY | 12.14 | 0 | 0 | 65
Total | [13 empty] | 24.02 | 0 | 0