## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | GARABAR PIPED WATER SUPPLY SCHEME. | SM/15850 | New | Material Requisition To Resource Division |  |  | RTOR000345/2022-2023 | 3010/TD | 27/02/2023 | 27/02/2023 | Resource Division | 16.31 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | GARABAR PIPED WATER SUPPLY SCHEME. | SM/15850 | New | Pump House, Laying distribution pipe line & Accommodate FHTC (50 nos) under JJM with allied work of GARA BAR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000839/2022-2023 | 3183/TD | 10/03/2023 | 06/09/2023 | BADAL CHANDRA GOLE | 18.58 | 12.06 | 64.9 | 70
3 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | GARABAR PIPED WATER SUPPLY SCHEME. | SM/15850 | New | Laying distribution pipe line, Boundary Wall & Accommodate FHTC (40 nos) under JJM with allied work of GARA BAR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART- C) | Assistant Engineer | Junior Engineer | ORD/000259/2023-2024 | 540/TD | 12/05/2023 | 31/05/2025 | CHANDA AGENCIES | 19.28 | 7.04 | 36.5 | 60
4 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | GARABAR PIPED WATER SUPPLY SCHEME. | SM/15850 | New | Material Requisition To Resource Division |  |  | RTOR000187/2023-2024 | 636/W | 20/02/2024 | 20/02/2024 | Resource Division | 0.92 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | GARABAR PIPED WATER SUPPLY SCHEME. | SM/15850 | New | Quotation bill of WBSEDCL for New Service Connection at Tube Well No.-1 of Garbar Water Supply Scheme under Tamluk Division, PHE Dte. |  |  | BILL/02147/2023-2024 | BP-2023-24-995 | 20/03/2024 | 20/03/2024 | WBSEDCL | 5.56 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | GARABAR PIPED WATER SUPPLY SCHEME. | SM/15850 | New | Quotation Bill for New Service connection at T/W NO-II Of GARABAR W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004601950/QUOT/03 DT. 15-02-2024 Application NO- 2004601950 Application type-New connection Reference Id- 204217839 |  |  | BILL/04265/2023-2024 |  | 01/03/2024 | 01/03/2024 | WBSEDCL | 6.61 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | GARABAR PIPED WATER SUPPLY SCHEME. | SM/15850 | New | Quotation Bill for New Service connection at T/W NO-I Of GARABAR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, MADHAKHALI C.C.C. Ref. Memo No- 2004625653/QUOT/03 DT. 01-03-2024 Application NO- 2004625653 Application type-New connection Consumer Id- 204232821 |  |  | BILL/04339/2023-2024 |  | 06/03/2024 | 06/03/2024 | WBSEDCL | 5.56 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | GARABAR PIPED WATER SUPPLY SCHEME. | SM/15850 | New | Payment of WBSEDCL for Quotation money for New Service Connection at Tube Well No. - II of Garbar Water Supply Scheme under Tamluk Division, PHE Dte. |  |  | BILL/00336/2024-2025 | BP-2024-25-113 | 10/05/2024 | 10/05/2024 | WBSEDCL | 6.61 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | GARABAR PIPED WATER SUPPLY SCHEME. | SM/15850 | New | Laying distribution pipe line & Accommodate FHTC (40 Nos) under JJM with allied work of GARA BAR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART- D) | Assistant Engineer | Junior Engineer | ORD/000126/2023-2024 | 262/TD | 19/04/2023 | 04/05/2023 | PARTHA CONSTRUCTION | 9.59 | 6.69 | 69.8 | 70
10 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | GARABAR PIPED WATER SUPPLY SCHEME. | SM/15850 | New | Pump House ,50 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (20 nos) under JJM with allied work of GARA BAR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART-A) | Assistant Engineer | Junior Engineer | ORD/000527/2023-2024 | 1776/TD | 02/08/2023 | 29/01/2024 | SUSIL KUMAR HAZRA | 68.66 | 0 | 0 | 35
11 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | GARABAR PIPED WATER SUPPLY SCHEME. | SM/15850 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 47 | 0.22 | 11
Total | [13 empty] | 21497.46 | 72.79 | 0.34