## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Contai-I | Tamluk Division | DESHHDUTTA BARH PIPED WATER SUPPLY SCHEME. | SM/15851 | New | Material Requisition To Resource Division |  |  | RTOR000348/2022-2023 | 3012/TD | 27/02/2023 | 27/02/2023 | Resource Division | 19.16 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Contai-I | Tamluk Division | DESHHDUTTA BARH PIPED WATER SUPPLY SCHEME. | SM/15851 | New | Material Requisition To Resource Division |  |  | RTOR000090/2024-2025 | 2956/TD | 12/09/2024 | 12/09/2024 | Resource Division | 1.54 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | DESHHDUTTA BARH PIPED WATER SUPPLY SCHEME. | SM/15851 | New | Deshduttabar W/S scheme T/W-I Application-no.-2004523550 Ref.-204157344 |  |  | BILL/03167/2023-2024 | BP-2023-24-446 | 19/12/2023 | 19/12/2023 | WBSEDCL | 0.13 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | DESHHDUTTA BARH PIPED WATER SUPPLY SCHEME. | SM/15851 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Contai - I and III in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000048/2023-2024 | 1205/W/MMD | 25/04/2023 | 31/08/2025 | BHABANI PRASAD MANNA | 57.85 | 0 | 0 | 60
5 | PURBA MEDINIPUR | Contai-I | Tamluk Division | DESHHDUTTA BARH PIPED WATER SUPPLY SCHEME. | SM/15851 | New | Pump House ,Rising main, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC (250 nos) under JJM with allied work of DESHHDUTTABARH PWSS within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000440/2023-2024 | 1424/TD | 12/07/2023 | 01/02/2025 | JASODA ENTERPRISE | 64.31 | 0 | 0 | 70
Total | [13 empty] | 142.99 | 0 | 0