## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | BADALPUR PIPED WATER SUPPLY SCHEME. | SM/15852 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Contai - I and III in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000048/2023-2024 | 1205/W/MMD | 25/04/2023 | 31/08/2025 | BHABANI PRASAD MANNA | 57.85 | 0 | 0 | 60
2 | PURBA MEDINIPUR | Contai-I | Tamluk Division | BADALPUR PIPED WATER SUPPLY SCHEME. | SM/15852 | New | Material Requisition To Resource Division |  |  | RTOR000346/2022-2023 | 3011/TD | 27/02/2023 | 27/02/2023 | Resource Division | 6.62 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Contai-I | Tamluk Division | BADALPUR PIPED WATER SUPPLY SCHEME. | SM/15852 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Badalpur PWSS at Ramnagar - II Block under Tamluk Division, PHE Dte. |  |  | ORD/000889/2023-2024 | 208/TD | 10/01/2024 | 20/01/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
4 | PURBA MEDINIPUR | Contai-I | Tamluk Division | BADALPUR PIPED WATER SUPPLY SCHEME. | SM/15852 | New | Material Requisition To Resource Division |  |  | RTOR000069/2024-2025 | 2947/TD | 12/09/2024 | 12/09/2024 | Resource Division | 1.53 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | BADALPUR PIPED WATER SUPPLY SCHEME. | SM/15852 | New | Quotation for new service connection at TW-1 of Badalpur ws scheme under MMD,PHE Dte. Block-Contai-I, Pichaboni CCC. Application no-2004641194. Con ID-204244743. |  |  | BILL/00009/2024-2025 | BP-2024-25-1 | 04/04/2024 | 04/04/2024 | WBSEDCL | 0.86 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | BADALPUR PIPED WATER SUPPLY SCHEME. | SM/15852 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Contai Sub Division and its adjacent Sub -Divisions under JJM Programe in the dist. of Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000512/2025-2026 | 876/HESD | 29/08/2025 | 29/08/2026 | S.S.GHORAI | 4.78 | 0 | 0 | 0
Total | [13 empty] | 72.59 | 0.95 | 1.31