## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-II | SM/15853 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bathuary Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000461/2022-2023 | 1860./TD | 21/11/2022 | 11/12/2022 | ASTER CONSULTANCY | 3.3 | 3.1 | 93.95 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-II | SM/15853 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 2071/TD | 28/08/2023 | 28/08/2023 | Resource Division | 15.21 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-II | SM/15853 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000101/2023-2024 | 3004/TD | 29/11/2023 | 29/11/2023 | Resource Division | 0.07 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Bathuari Zone-II | SM/15853 | Augmentation | Quotation Bill for New Service connection at T/W NO-I, Zone-II Of BATHUARY W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004732398/QUOT/03/213 DT. 15-05-2024 Application NO- 2004732398 Application type-New connection Consumer Id- 204305458 |  |  | BILL/01131/2024-2025 | BP-2024-25-247 | 06/06/2024 | 06/06/2024 | WBSEDCL | 6.88 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Bathuari Zone-II | SM/15853 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at at different PWSS of Block Egra - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000073/2023-2024 | 1242/W/MMD | 28/04/2023 | 31/05/2025 | BHABANI PRASAD MANNA | 84.29 | 0 | 0 | 70
6 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-II | SM/15853 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (24 nos) under JJM with allied work for Bathuari (Zone-II) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000524/2023-2024 | 1760/TD | 01/08/2023 | 01/12/2025 | ARABINDA GHOSH | 294.32 | 102.26 | 34.74 | 50
7 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-II | SM/15853 | Augmentation | Land Developing at Head Work site & 2nd Tube well site for Augmentation of Bathuary (Zone-II) Water Supply Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000297/2024-2025 | 3066/TD | 19/09/2024 | 09/10/2024 | GHOSH ENTERPRISE | 9.46 | 0 | 0 | 100
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Bathuari Zone-II | SM/15853 | Augmentation | Quotation Bill for New Service connection at T/W NO-II, ZONE-II Of BATHUARY W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2005007909/QUOT/03 DT. 14-12-2024 Application NO- 2005007909 Application type-New connection Consumer Id- 204472925 |  |  | BILL/03684/2024-2025 | C012524069662 | 09/01/2025 | 09/01/2025 | WBSEDCL | 7.1 | 0 | 0 | 0
Total | [13 empty] | 420.62 | 105.36 | 25.05