## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme | SM/16194 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. [PART-III] | Assistant Engineer | Junior Engineer | ORD/000455/2022-2023 | 1855./TD | 21/11/2022 | 11/12/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.61 | 3.23 | 89.5 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme | SM/16194 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 2637/TD | 13/10/2023 | 13/10/2023 | Resource Division | 8.79 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme | SM/16194 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 2095/TD | 29/08/2023 | 29/08/2023 | Resource Division | 156.45 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme | SM/16194 | Augmentation | Withdrawing and Relaying of different dia D.I pipe line at Contai Saline Area Zone-IV PART-III Water Supply Scheme due to Widening and Strengthening along existing alignment of Contai-Rasulpur Road under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer |  | ORD/000114/2024-2025 | 1907/TD | 07/06/2024 | 02/07/2024 | TARUN KHATUA | 43.11 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme | SM/16194 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Contai - I and III in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000048/2023-2024 | 1205/W/MMD | 25/04/2023 | 31/08/2025 | BHABANI PRASAD MANNA | 57.85 | 0 | 0 | 60
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme | SM/16194 | Augmentation | Laying distribution pipe line, & Accommodate FHTC (1427 nos) under JJM with allied work for Augmentation of Contai Saline Area Zone-IV PART-III PWSS in Deshapran Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000405/2023-2024 | 1091/TD | 08/06/2023 | 21/06/2026 | SUJATA CONSTRUCTION | 214.81 | 84.58 | 39.38 | 50
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme | SM/16194 | Augmentation | Repairing of Switch Room cum Chlorin Room at 2nd TW site for Augmentation of Contai Saline Area Zoner-IV Part-III Water Supply Scheme within Deshpran Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer |  | ORD/000370/2024-2025 | 3399/TD | 28/10/2024 | 27/11/2024 | SUBRATA KUMAR BERA | 1.8 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme | SM/16194 | Augmentation | Repairing of OHR, Pump House no 1 and Head Works Boundary Wall under JJM with allied work of Contai Saline Area Zone-IV Part-III PWSS within Contai-II(Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000293/2024-2025 | 3058/TD | 19/09/2024 | 29/10/2024 | SOUMEN KUMAR GHOSH | 29.17 | 0 | 0 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme | SM/16194 | Augmentation | Relaying of Damaged Distribution Pipe Line due to Paka Drain work by PWD with allied Works for Contai Saline Area Zone-IV Water Supply Scheme within Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000407/2024-2025 | 3468/TD | 06/11/2024 | 26/11/2024 | FARID UDDIN AHMED | 3.19 | 3.03 | 94.81 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Contai Saline Area Zone-IV Part-III Piped Water Supply Scheme | SM/16194 | Augmentation | Installation of display Board of Haipur Retrofitting PWSS at 2 nos TW site in Contai - I Block , Contai S.A. ZONE - IV (PART- I ) PWSS at 1 nos TW site , Contai S.A. ZONE - IV (PART-III) PWSS at 2 nos TW site, in Deshpran Block for JJM works for Open Land within Contai Sub-Division under Tamluk Division, PHE Dte. PurbaMedinipurDistrict. | Assistant Engineer | Junior Engineer | ORD/000300/2025-2026 | 1599/CSD | 19/06/2025 | 26/06/2025 | BISWA NIRMAN ENTERPRISE. | 0.83 | 0 | 0 | 100
Total | [13 empty] | 519.62 | 90.84 | 17.48