## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-II | Tamluk Division | BANCHBERA AND ITS ADJOINING MOUJAS PWSS | SM/16200 | New | Material Requisition To Resource Division |  |  | RTOR000352/2022-2023 | 3015/TD | 27/02/2023 | 27/02/2023 | Resource Division | 16.09 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-II | Tamluk Division | BANCHBERA AND ITS ADJOINING MOUJAS PWSS | SM/16200 | New | Laying distribution pipe line, Boundary Wall & Rising main pipe line under JJM with allied work for BANCHBERA PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000125/2023-2024 | 257/TD | 19/04/2023 | 18/06/2023 | SOUMYA ENTERPRISE | 49.45 | 20.51 | 41.47 | 45
3 | PURBA MEDINIPUR | Egra-II | Tamluk Division | BANCHBERA AND ITS ADJOINING MOUJAS PWSS | SM/16200 | New | Laying distribution pipe line, Pump House , & Accommodate FHTC (147 nos) under JJM with allied work for BANCHBERA PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000123/2023-2024 | 256/TD | 19/04/2023 | 23/08/2025 | CHANDIMATA CONSTRUCTION | 84.7 | 26.51 | 31.3 | 70
4 | PURBA MEDINIPUR | Egra-II | Tamluk Division | BANCHBERA AND ITS ADJOINING MOUJAS PWSS | SM/16200 | New | Soil investigation, 50 cum OHR ( type with pile foundation) under JJM with allied work for BANCHBERA PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-C) | Assistant Engineer | Junior Engineer | ORD/000416/2023-2024 | 1085/TD | 08/06/2023 | 05/12/2023 | GOUTAM CONSTRUCTION | 38.56 | 31.16 | 80.79 | 50
5 | PURBA MEDINIPUR | Egra-II | Tamluk Division | BANCHBERA AND ITS ADJOINING MOUJAS PWSS | SM/16200 | New | Material Requisition To Resource Division |  |  | RTOR000023/2025-2026 | 2085/TD | 12/08/2025 | 12/08/2025 | Resource Division | 0.91 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Egra-II | Tamluk Division | BANCHBERA AND ITS ADJOINING MOUJAS PWSS | SM/16200 | New | Quotation Bill for New Service connection at T/W NO-II Of BANCHBERIA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004671953/QUOT/03/49 DT. 05-04-2024 Application NO- 2004671953 Application type-New connection Consumer Id- 204266734 |  |  | BILL/01293/2024-2025 | BP-2024-25-653 | 06/02/2025 | 06/02/2025 | WBSEDCL | 2.96 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Egra-II | Tamluk Division | BANCHBERA AND ITS ADJOINING MOUJAS PWSS | SM/16200 | New | Quotation Bill for New Service connection at T/W NO-I Of BANCHBERIA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004672038/QUOT/03/51 DT. 05-04-2024 Application NO- 2004672038 Application type-New connection Consumer Id- 204266721 |  |  | BILL/01294/2024-2025 | BP-2024-25-654 | 06/02/2025 | 06/02/2025 | WBSEDCL | 5.11 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Egra-II | Central Drilling | BANCHBERA AND ITS ADJOINING MOUJAS PWSS | SM/16200 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 57.54 | 0.27 | 11
Total | [13 empty] | 21537.53 | 135.72 | 0.63