## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-II | Tamluk Division | BANCHBERA AND ITS ADJOINING MOUJAS PWSS | SM/16200 | New | Material Requisition To Resource Division |  |  | RTOR000352/2022-2023 | 3015/TD | 27/02/2023 | 27/02/2023 | Resource Division | 16.09 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-II | Tamluk Division | BANCHBERA AND ITS ADJOINING MOUJAS PWSS | SM/16200 | New | Laying distribution pipe line, Boundary Wall & Rising main pipe line under JJM with allied work for BANCHBERA PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000125/2023-2024 | 257/TD | 19/04/2023 | 18/06/2023 | SOUMYA ENTERPRISE | 49.45 | 20.51 | 41.47 | 45
3 | PURBA MEDINIPUR | Egra-II | Tamluk Division | BANCHBERA AND ITS ADJOINING MOUJAS PWSS | SM/16200 | New | Laying distribution pipe line, Pump House , & Accommodate FHTC (147 nos) under JJM with allied work for BANCHBERA PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000123/2023-2024 | 256/TD | 19/04/2023 | 23/08/2025 | CHANDIMATA CONSTRUCTION | 84.7 | 26.51 | 31.3 | 70
4 | PURBA MEDINIPUR | Egra-II | Tamluk Division | BANCHBERA AND ITS ADJOINING MOUJAS PWSS | SM/16200 | New | Soil investigation, 50 cum OHR ( type with pile foundation) under JJM with allied work for BANCHBERA PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-C) | Assistant Engineer | Junior Engineer | ORD/000416/2023-2024 | 1085/TD | 08/06/2023 | 05/12/2023 | GOUTAM CONSTRUCTION | 38.56 | 31.16 | 80.79 | 50
Total | [13 empty] | 188.8 | 78.17 | 41.41