## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | PANCHBERYA PIPED WATER SUPPLY SCHEME | SM/16201 | New | Material Requisition To Resource Division |  |  | RTOR000347/2022-2023 | 3017/TD | 27/02/2023 | 27/02/2023 | Resource Division | 7.21 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | PANCHBERYA PIPED WATER SUPPLY SCHEME | SM/16201 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at PANCHBERYA PIPED WATER SUPPLY SCHEME in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000045/2023-2024 | 1217/W/MMD | 25/04/2023 | 22/10/2023 | BHABANI PRASAD MANNA | 11.87 | 0 | 0 | 40
3 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | PANCHBERYA PIPED WATER SUPPLY SCHEME | SM/16201 | New | Material Requisition To Resource Division |  |  | RTOR000162/2023-2024 | 116/TD | 05/01/2024 | 05/01/2024 | Resource Division | 0.81 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | PANCHBERYA PIPED WATER SUPPLY SCHEME | SM/16201 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, soil investigation , 50 cum OHR & Accommodate FHTC (131 nos) under JJM with allied work for PANCHBERRYA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000513/2023-2024 | 1742/TD | 01/08/2023 | 20/07/2025 | S.D. CONSTRUCTION | 141.9 | 0 | 0 | 0
Total | [13 empty] | 161.79 | 0 | 0