## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-I | Tamluk Division | BHATSALIA & IT'S ADJOINING MOUJAS PWSS | SM/16203 | New | Material Requisition To Resource Division |  |  | RTOR000351/2022-2023 | 3014/TD | 27/02/2023 | 27/02/2023 | Resource Division | 9.41 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-I | Tamluk Division | BHATSALIA & IT'S ADJOINING MOUJAS PWSS | SM/16203 | New | Laying distribution pipe line, Boundary Wall under JJM with allied work for BHATSALIA PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000446/2023-2024 | 1454/TD | 13/07/2023 | 27/08/2023 | MAHAPRABHU ENTERPRISE | 14.4 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Egra-I | Tamluk Division | BHATSALIA & IT'S ADJOINING MOUJAS PWSS | SM/16203 | New | Quotation for new service connection at TW-1 of Bhatsalia ws scheme under MMD,PHE Dte, Block-Egra-1, Chorpalia CCC Application no-2004753843 CON ID-204318364 |  |  | BILL/00595/2024-2025 | BP-2024-25-292 | 29/07/2024 | 29/07/2024 | WBSEDCL | 5.37 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Egra-I | Tamluk Division | BHATSALIA & IT'S ADJOINING MOUJAS PWSS | SM/16203 | New | Quotation for new service connection at t/w no.-II of Bhatsalia ws scheme under MMD,PHE Dte, Block-Egra-1, Chorpalia CCC Application no-2004753851 Con ID-204322327 |  |  | BILL/00593/2024-2025 | BP-2024-25-293 | 29/07/2024 | 29/07/2024 | WBSEDCL | 4.56 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Egra-I | Tamluk Division | BHATSALIA & IT'S ADJOINING MOUJAS PWSS | SM/16203 | New | Soil investigation, Construction of 50 cum OHR (tourch type with pile foundation) under JJM with allied work for Bhatsalia PWSS within Egra-I Block including Supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-D) | Assistant Engineer | Junior Engineer | ORD/000417/2023-2024 | 1086/TD | 08/06/2023 | 05/12/2023 | GOUTAM CONSTRUCTION | 38.57 | 0 | 0 | 30
6 | PURBA MEDINIPUR | Egra-I | Tamluk Division | BHATSALIA & IT'S ADJOINING MOUJAS PWSS | SM/16203 | New | Laying distribution pipe line, Pump House , Boundary Wall & Accommodate FHTC (337 nos) under JJM with allied work for BHATSALIA PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000445/2023-2024 | 1453/TD | 13/07/2023 | 16/04/2025 | R CONSTRUCTION | 78.02 | 38.07 | 48.8 | 85
7 | PURBA MEDINIPUR | Egra-I | Tamluk Division | BHATSALIA & IT'S ADJOINING MOUJAS PWSS | SM/16203 | New | Material Requisition To Resource Division |  |  | RTOR000012/2025-2026 | 2070/TD | 12/08/2025 | 12/08/2025 | Resource Division | 2.08 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Egra-I | Central Drilling | BHATSALIA & IT'S ADJOINING MOUJAS PWSS | SM/16203 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 46.63 | 0.22 | 11
Total | [13 empty] | 21492.16 | 84.7 | 0.39