## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Manikpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/16205 | Augmentation | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Jalpai Part-II W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Tajpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Manikpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000017/2023-2024 | 115/TD | 06/04/2023 | 16/05/2023 | B. K. ENTERPRISE | 63.13 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) Nos. Boosting Tube Well for Manikpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/16205 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 353/TD | 26/04/2023 | 26/04/2023 | Resource Division | 0.63 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Manikpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/16205 | Augmentation | Electric Quotation for MANIKPUR Boosting, Water Supply Scheme T/W (Ref. ID-204063673) |  |  | BILL/01822/2023-2024 | BP-2023-24-203 | 24/08/2023 | 24/08/2023 | WBSEDCL | 4.87 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Manikpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/16205 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Nandigram I & II and Panskura - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000051/2023-2024 | 1209/W/MMD | 25/04/2023 | 22/10/2023 | BHABANI PRASAD MANNA | 53.9 | 0 | 0 | 35
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Manikpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/16205 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001532/2023-2024 | 949/HESD | 30/11/2023 | 29/02/2024 | S.S.GHORAI | 0.45 | 0 | 0 | 100
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Manikpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/16205 | Augmentation | Additional Quotation of Manikpur Boosting Tube Well Application ID-100000095367 Referance ID- 860287817 |  |  | BILL/03181/2023-2024 | BP-2023-24-467 | 27/12/2023 | 27/12/2023 | WBSEDCL | 0.29 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | 1 (One) Nos. Boosting Tube Well for Manikpur Water Supply Scheme of Nandigram-I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/16205 | Augmentation | Continuation order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000294/2024-2025 | 484/HESD | 28/05/2024 | 27/08/2024 | S.S.GHORAI | 0.45 | 0 | 0 | 100
Total | [13 empty] | 123.72 | 0 | 0