## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Contai - I | Tamluk Division | BATIPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16257 | New | Material Requisition To Resource Division |  |  | RTOR000249/2022-2023 | 2717/TD | 06/02/2023 |  | Resource Division | 42.25 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Contai - I | Midnapore Mechanical | BATIPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16257 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BATIPUR AND ITS ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/002039/2022-2023 | 947/W/MMD | 28/03/2023 | 24/09/2023 | A.S.ENTERPRISE | 21.57 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Contai - I | Tamluk Division | BATIPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16257 | New | Sinking Tube well ,Construction of Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (958 nos), Including 2 years of Operation maintance under JJM with allied work of BATIPUR PWSS within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000404/2023-2024 | 1092/TD | 08/06/2023 | 05/12/2023 | SUJATA CONSTRUCTION | 368.76 | 23.86 | 6.47 | 15
Total | [13 empty] | 432.58 | 23.86 | 5.52