## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Piped water Supply Scheme for Chirulia-Chatla Zone-1 | SM/16284 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 2993/TD | 29/11/2023 | 29/11/2023 | Resource Division | 1 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Piped water Supply Scheme for Chirulia-Chatla Zone-1 | SM/16284 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 2062/TD | 28/08/2023 | 28/08/2023 | Resource Division | 13.54 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Piped water Supply Scheme for Chirulia-Chatla Zone-1 | SM/16284 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 162 Nos) under JJM with allied work for Chirulia-Chatla (Zone-I) PWSS within Egra-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000408/2023-2024 | 1088/TD | 08/06/2023 | 01/12/2025 | AJIT KUMAR SOM | 269.22 | 0 | 0 | 60
4 | PURBA MEDINIPUR |  | Tamluk Division | Piped water Supply Scheme for Chirulia-Chatla Zone-1 | SM/16284 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chirulia Chatla Water Supply Scheme under Tamluk Division, PHE Dte. ( PART- I ) | Assistant Engineer | Junior Engineer | ORD/000965/2022-2023 | 1055/TD | 18/08/2022 | 07/09/2022 | ASTER CONSULTANCY | 4.01 | 0 | 0 | 100
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped water Supply Scheme for Chirulia-Chatla Zone-1 | SM/16284 | Augmentation | Quotation For New Service Connections at Tube Well-I of Chirulia Chalta, Zone-I W/S scheme under MMD PHE Dte. Chorepalia CCC Block- Egra-I Application No.-2004746276 Consumer ID.-204313776 Application Date.-29/05/2024 |  |  | BILL/01137/2024-2025 | BP-2024-25-254 | 06/06/2024 | 06/06/2024 | WBSEDCL | 13.67 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped water Supply Scheme for Chirulia-Chatla Zone-1 | SM/16284 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Egra - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000050/2023-2024 | 1207/W/MMD | 25/04/2023 | 31/12/2025 | BHABANI PRASAD MANNA | 59.85 | 0 | 0 | 20
Total | [13 empty] | 361.28 | 0 | 0