## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV | SM/16286 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000458/2022-2023 | 1857/TD | 21/11/2022 | 11/12/2022 | ASTER CONSULTANCY | 3.46 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV | SM/16286 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 2068/TD | 28/08/2023 | 28/08/2023 | Resource Division | 13.67 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV | SM/16286 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000102/2023-2024 | 3005/TD | 29/11/2023 | 29/11/2023 | Resource Division | 1.29 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV | SM/16286 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Kanpur Zone- IV PWSS at Ramnagar - II Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000869/2023-2024 | 191/TD | 10/01/2024 | 20/01/2024 | ASTER CONSULTANCY | 0.95 | 0 | 0 | 100
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV | SM/16286 | Augmentation | Kanpur W/S scheme T/W-I, Zone-IV Application No.-2004536085 Ref.-204168169 |  |  | BILL/03290/2023-2024 | BP-2023-24-542 | 11/01/2024 | 11/01/2024 | WBSEDCL | 3.6 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV | SM/16286 | Augmentation | Kanpur W/S scheme PH-II, Zone-IV Application No.-2004565701 Ref no.-204193734 |  |  | BILL/03521/2023-2024 | BP-2023-24-587 | 02/02/2024 | 02/02/2024 | WBSEDCL | 4.96 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV | SM/16286 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000052/2023-2024 | 1216/W/MMD | 25/04/2023 | 30/09/2025 | BHABANI PRASAD MANNA | 83.38 | 0 | 0 | 34
8 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV | SM/16286 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 209 Nos) under JJM with allied work for KANPUR (Zone-IV) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000508/2023-2024 | 1730/TD | 31/07/2023 | 28/09/2025 | ONKAR ENTERPRISE | 308.34 | 0 | 0 | 40
9 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-IV | SM/16286 | Augmentation | Drum Sheet walling, road restoration for distribution pipe line ( for FHTC) & Accommodate FHTC (130Nos) under JJM with allied work for KANPUR (Zone -IV) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000316/2024-2025 | 3183/TD | 30/09/2024 | 28/05/2025 | GHOSH CONSTRUCTION | 95.27 | 0 | 0 | 85
Total | [13 empty] | 514.93 | 0 | 0