## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Western) Water Supply Scheme. | SM/16288 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Digha Water Supply Scheme (Western Zone) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000443/2021-2022 | .1652/TD | 20/01/2022 | 09/02/2022 | HORIZEN | 3.2 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Western) Water Supply Scheme. | SM/16288 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 2639/TD | 13/10/2023 | 13/10/2023 | Resource Division | 4.82 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Western) Water Supply Scheme. | SM/16288 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 2065/TD | 28/08/2023 | 28/08/2023 | Resource Division | 29.47 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Western) Water Supply Scheme. | SM/16288 | Augmentation | Quotation for new service connection at T/W-IV of Digha western zone under MMD,PHE DTE, Block-Ramnagar-I, DIGHA CCC Application no-2004812623 CON ID-204351922 |  |  | BILL/01583/2024-2025 | BP-2024-25-457 | 23/07/2024 | 23/07/2024 | WBSEDCL | 0.92 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Western) Water Supply Scheme. | SM/16288 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (782 nos) under JJM with allied work for Digha Augmentation (Western Zone) PWSS within Ramnagar-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000484/2023-2024 | 1569/TD | 19/07/2023 | 01/07/2025 | GUHA CONSTRUCTION | 355.55 | 0 | 0 | 16
Total | [13 empty] | 393.96 | 0 | 0