## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V | SM/16295 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme (Zone-V) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000459/2022-2023 | 1858/TD | 21/11/2022 | 11/12/2022 | ASTER CONSULTANCY | 3.3 | 3.13 | 94.86 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V | SM/16295 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000094/2023-2024 | 2997/TD | 29/11/2023 | 29/11/2023 | Resource Division | 1.13 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V | SM/16295 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 2067/TD | 28/08/2023 | 28/08/2023 | Resource Division | 13.54 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V | SM/16295 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 184 Nos) under JJM with allied work for KANPUR (Zone-V) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000509/2023-2024 | 1731/TD | 31/07/2023 | 01/04/2025 | ONKAR ENTERPRISE | 284.7 | 166.43 | 58.46 | 5
5 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V | SM/16295 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Kanpur Zone-V PWSS at Ramnagar - II Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000868/2023-2024 | 190/TD | 10/01/2024 | 20/01/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V | SM/16295 | Augmentation | Payment to WBSEDCL for Shifting of 33 KV FEEDER HT Line at Sabitrapur for Kanpur Water Supply Scheme for Zone-V under Tamluk Division, PHE Dte. |  |  | BILL/02086/2023-2024 | BP-2023-24-957 | 14/03/2024 | 14/03/2024 | WBSEDCL | 3.05 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V | SM/16295 | Augmentation | Kanpur W/S scheme TW no.-II, Z-V Ref.-204156068 Application ID-2004521673 |  |  | BILL/03154/2023-2024 | BP-2023-24-445 | 19/12/2023 | 19/12/2023 | WBSEDCL | 2.57 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V | SM/16295 | Augmentation | Quotation for new service connection at TW-I,ZONE-V of KANPUR WS SCHEME under MMD,PHE Dte, Block-Ramnagar-II, DIGHA CCC, Application no-2004644488, CON ID-204246837 |  |  | BILL/04741/2023-2024 | BP-2023-24-913 | 28/03/2024 | 28/03/2024 | WBSEDCL | 4.81 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V | SM/16295 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000052/2023-2024 | 1216/W/MMD | 25/04/2023 | 30/09/2025 | BHABANI PRASAD MANNA | 83.38 | 0 | 0 | 34
10 | PURBA MEDINIPUR |  | Tamluk Division | PIPED WATER SUPPLY SCHEME FOR KANPUR-ZONE-V | SM/16295 | Augmentation | Drum Sheet walling, road restoration for distribution pipe line ( for FHTC) & Accommodate FHTC (215 Nos) under JJM with allied work for KANPUR (Zone-V) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000591/2024-2025 | 491/TD | 06/02/2025 | 06/06/2025 | GHOSH CONSTRUCTION | 87.4 | 0 | 0 | 80
Total | [13 empty] | 484.83 | 170.51 | 35.17