## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-III | SM/16300 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bathuary Water Supply Scheme (Zone-III) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000462/2022-2023 | 1861./TD | 21/11/2022 | 11/12/2022 | ASTER CONSULTANCY | 3.3 | 2.89 | 87.53 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-III | SM/16300 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2023-2024 | 2072/TD | 28/08/2023 | 28/08/2023 | Resource Division | 15.35 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-III | SM/16300 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000100/2023-2024 | 3003/TD | 29/11/2023 | 29/11/2023 | Resource Division | 0.34 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Bathuari Zone-III | SM/16300 | Augmentation | Quotation Bill for New Service connection at T/W NO-II, Zone-III Of BATHUARY W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004793307/QUOT/03/380 DT. 02-07-2024 Application NO- 2004793307 Application type-New connection Consumer Id- 204346846 |  |  | BILL/01698/2024-2025 | BP-2024-25-497 | 31/07/2024 | 31/07/2024 | WBSEDCL | 3.96 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Bathuari Zone-III | SM/16300 | Augmentation | Quotation Bill for New Service connection at T/W NO-I Of BARHUARY ZIII W/S Scheme under MMD, PHE, Dte. Block- EGRA II, WBSEDCL SUPPLY OFFICE: BALIGHAIC.C.C. Ref. Memo No- 2004737554/QUOT/03 DT. 16-05-2024 Application NO- 2004737554 Application type-New connection Consumer Id- 204309058 |  |  | BILL/01227/2024-2025 | BP-2024-25-292 | 18/06/2024 | 18/06/2024 | WBSEDCL | 3.27 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Bathuari Zone-III | SM/16300 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at at different PWSS of Block Egra - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000073/2023-2024 | 1242/W/MMD | 28/04/2023 | 31/05/2025 | BHABANI PRASAD MANNA | 84.29 | 0 | 0 | 70
7 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Bathuari Zone-III | SM/16300 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (55 nos) under JJM with allied work for Bathuari (Zone-III) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000525/2023-2024 | 1761/TD | 01/08/2023 | 01/12/2025 | ARABINDA GHOSH | 261.16 | 58.13 | 22.26 | 80
Total | [13 empty] | 371.66 | 61.02 | 16.42