## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-IV | SM/16305 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 2070/TD | 28/08/2023 | 28/08/2023 | Resource Division | 14.46 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-IV | SM/16305 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 2999/TD | 29/11/2023 | 29/11/2023 | Resource Division | 1.81 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-IV | SM/16305 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 294 Nos) under JJM with allied work for SANKARPUR (Zone-IV) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000510/2023-2024 | 1732/TD | 31/07/2023 | 27/03/2026 | ONKAR ENTERPRISE | 216.84 | 69.71 | 32.15 | 55
4 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-IV | SM/16305 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone- IV) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000331/2023-2024 | 741/TD | 25/05/2023 | 14/06/2023 | ASTER CONSULTANCY | 3.46 | 3.46 | 100 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-IV | SM/16305 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Sankarpur Z-IV PWSS at Ramnagar-I Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001281/2023-2024 | 1053/TD | 15/03/2024 | 25/03/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-IV | SM/16305 | Augmentation | Sankarpur W/S scheme PH.-II, zone-IV Application No.-2004565718 Ref.-204193727 |  |  | BILL/03540/2023-2024 | BP-2023-24-622 | 07/02/2024 | 07/02/2024 | WBSEDCL | 7.26 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-IV | SM/16305 | Augmentation | Sankarpur W/S scheme TW no.-I, Z-IV Ref.-204156071 Application ID-2004521698 |  |  | BILL/03156/2023-2024 | BP-2023-24-442 | 19/12/2023 | 19/12/2023 | WBSEDCL | 2.63 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Sankarpur Zone-IV | SM/16305 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments atPiped Water Supply Scheme for Sankarpur Zone-IV in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000041/2023-2024 | 1212/W/MMD | 25/04/2023 | 22/10/2023 | SUBHASIS ROY | 23.93 | 22.24 | 92.93 | 90
9 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Sankarpur Zone-IV | SM/16305 | Augmentation | Laying distribution pipe line Due to Re-design & Accommodate Balance FHTC ( 125 Nos) under JJM with allied work for SANKARPUR (Zone-IV) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000513/2024-2025 | 3943/TD | 23/12/2024 | 13/03/2025 | ONKAR ENTERPRISE | 32.85 | 0 | 0 | 100
Total | [13 empty] | 304.2 | 96.36 | 31.68